## ProjectMilestones
Milestone_ID | Project_ID | Milestone_Name | Planned_Date | Actual_Date | Status
M5001 | P1001 | Final Handover | 2026-02-02 | 2026-04-03 | Completed
M5002 | P1001 | Foundation | 2026-03-26 | 2026-04-30 | Completed
M5003 | P1001 | Structural Work | 2026-05-17 | 2026-07-16 | Completed
M5004 | P1001 | Safety Inspection | 2026-07-08 | 2026-08-12 | Completed
M5005 | P1001 | Land Acquisition | 2026-08-29 | 2026-09-08 | Completed
M5006 | P1002 | Major Construction | 2023-02-26 |  | Not Started
M5007 | P1002 | Safety Inspection | 2023-05-25 | 2023-06-04 | Completed
M5008 | P1002 | Design Approval | 2023-08-22 |  | Pending
M5009 | P1002 | Land Acquisition | 2023-11-18 | 2023-11-18 | Completed
M5010 | P1002 | Structural Work | 2024-02-15 | 2024-04-15 | Delayed
M5011 | P1002 | Testing | 2024-05-13 | 2024-06-17 | Completed
M5012 | P1003 | Design Approval | 2023-11-11 | 2024-01-10 | Completed
M5013 | P1003 | Land Acquisition | 2024-03-18 | 2023/99/10 | Completed
M5014 | P1003 | Safety Inspection | 2024-07-24 | 2024-08-13 | Delayed
M5015 | N/A | Final Handover | 2024-11-29 |  | In Progress
M5016 | P1003 | Structural Work | 2025-04-06 | 2025-04-16 | Delayed
M5017 | P1003 | Testing | 2025-08-12 | 2025-08-14 | Completed
M5018 | P1004 | Major Construction | 2025-05-26 | 2025-06-05 | Delayed
M5019 | P1004 | Structural Work | 2025-08-14 | 2025-08-19 | Delayed
M5020 | P1004 | Design Approval | 2025-11-02 | 2025-11-04 | Completed
M5021 | P1004 | Land Acquisition | 2026-01-22 | 2026-03-23 | Completed
M5022 | P1004 | Testing | 2026-04-12 | 2026-06-11 | Completed
M5023 | P1004 | Foundation | 2026-07-01 | 2026-08-30 | Delayed
M5024 | P1005 | Testing | 2024-09-23 |  | Pending
M5025 | P1005 | N/A | 2025-01-21 |  | In Progress
M5026 | P1005 | Foundation | 2025-05-20 | 2025-05-30 | Completed
M5027 | P1005 | Design Approval | 2025-09-17 |  | Pending
M5028 | P1005 | Land Acquisition | 2026-01-14 |  | Pending
M5029 | P1005 | Major Construction | 2026-05-14 | 2026-05-16 | Completed
M5030 | P1006 | Structural Work | 2025-07-06 |  | Pending
M5031 | P1006 | Major Construction | 2025-09-05 | 2025-09-25 | Completed
M5032 | P1006 | Final Handover | 2025-11-05 |  | Not Started
M5033 | P1006 | Foundation | 2026-01-05 | 2026-01-25 | Completed
M5034 | P1007 | Foundation | 2022-11-02 | 2022-11-02 | Completed
M5035 | P1007 | Major Construction | 2023-01-18 | 2023-01-20 | Completed
M5036 | P1007 | Design Approval | 2023-04-05 | 2023-04-05 | Completed
M5037 | P1007 | Structural Work | 2023-06-21 |  | Pending
M5038 | P1007 | Final Handover | 2023-09-06 |  | In Progress
M5039 | P1007 | Land Acquisition | 2023-11-22 |  | In Progress
M5040 | P1008 | Land Acquisition | N/A |  | Not Started
M5041 | P1008 | Design Approval | 2026-05-31 |  | Pending
M5042 | P1008 | Major Construction | 2026-10-30 | 2026-12-04 | Delayed
M5043 | P1008 | Safety Inspection | 2027-03-31 |  | In Progress
M5044 | P1009 | Testing | 2022-11-13 | 2022-12-18 | Completed
M5045 | P1009 | Design Approval | 2023-02-08 | 2023-02-28 | Completed
M5046 | P1009 | Safety Inspection | 2023-05-06
M5047 | P1009 | Structural Work | 2023-08-02 | 2023-09-06 | Completed
M5048 | N/A | Major Construction | 2023-10-28 |  | Not Started
M5049 | P1009 | Foundation | 2024-01-23 | 2024-03-23 | Completed
M5050 | P1010 | Testing | 2022-11-15 |  | Pending
M5051 | P1010 | Safety Inspection | 2023-01-16 | 2023-01-16 | Completed
M5052 | P1010 | Major Construction | 2023-03-19 | 2023-03-24 | Completed
M5053 | P1010 | Design Approval | 2023-05-20 | 2023-06-15 | Delayed
M5054 | P1010 | Land Acquisition | 2023-07-21 |  | Not Started
M5055 | P1011 | Final Handover | 2024-08-07 | 2024-08-12 | Completed
M5056 | P1011 | Land Acquisition | 2024-12-17 |  | Pending
M5057 | P1011 | Foundation | 2025-04-29 | 2025-06-03 | Delayed
M5058 | P1011 | Design Approval | 2025-09-08 |  | In Progress
M5059 | P1011 | Major Construction | 2026-01-19 | 2026-01-29 | Completed
M5060 | P1011 | Testing | 2026-05-31 | 2026-05-31 | Delayed
M5061 | P1012 | Foundation | 2022-03-08 | 2022-03-13 | Completed
M5062 | P1012 | Structural Work | 2022-04-29 | 2022-05-01 | Delayed
M5063 | P1012 | Land Acquisition | 2022-06-20 | 2022-06-20 | Completed
M5064 | P1012 | Testing | 2022-08-11 | 2022-08-31 | Delayed
M5065 | P1012 | Final Handover | 2022-10-02 | 2022-12-11 | Delayed
M5066 | P1013 | Safety Inspection | 2023-02-12 | 2023-02-14 | Delayed
M5067 | P1013 | Design Approval | 2023-06-29 |  | Not Started
M5068 | P1013 | Land Acquisition | 2023-11-14 |  | Not Started
M5069 | P1013 | Testing | 2024-03-30 | 2024-04-04 | Completed
M5070 | P1013 | Foundation | 2024-08-14 | 2024-08-14 | Delayed
M5071 | P1014 | Foundation | 2022-08-15 |  | Not Started
M5072 | P1014 | Land Acquisition | 2022-12-09 | 2023-01-18 | Delayed
M5073 | P1014 | Final Handover | 2023-04-04 | 2023-04-06 | Completed
M5074 | P1014 | Safety Inspection | 2023-07-29 | 2023-08-23 | Delayed
M5075 | P1014 | Structural Work | 2023-11-22 | 2023-11-22 | Completed
M5076 | P1014 | Major Construction | 2024-03-17 | 2024-05-31 | Delayed
M5077 | P1014 | Design Approval | 2024-07-11 | 2024-08-15 | Completed
M5078 | P1015 | Safety Inspection | 2023-04-26 | 2023-05-06 | Completed
M5079 | P1015 | Design Approval | 2023-08-09 | 2023-08-19 | Completed
M5080 | P1015 | Foundation | 2023-11-22 | 2023-11-27 | Completed
M5081 | P1015 | Structural Work | 2024-03-06 |  | Completed
M5082 | P1016 | Testing | 2023-04-17 |  | Not Started
M5083 | P1016 | Safety Inspection | 2023-08-26 | 2023-08-26 | Delayed
M5084 | P1016 | Major Construction | 2024-01-04 |  | In Progress
M5085 | P1016 | Structural Work | 2024-05-14 |  | Not Started
M5086 | P1017 | Structural Work | 2026-03-08 | 2026-03-28 | Completed
M5087 | N/A | Final Handover | 2026-06-17 | 2026-08-16 | Delayed
M5088 | P1017 | Foundation | 2026-09-26 | 2026-09-28 | Completed
M5089 | P1017 | Land Acquisition | 2027-01-05 |  | Pending
M5090 | P1017 | Safety Inspection | 2027-04-16 | 2027-04-16 | N/A
M5091 | P1017 | Testing | 2027-07-26 | 2027-09-24 | Completed
M5092 | P1017 | Major Construction | 2027-11-04 |  | In Progress
M5093 | P1018 | Design Approval | 2025-07-24 | 2025-07-29 | Delayed
M5094 | P1018 | Land Acquisition | 2025-11-05 |  | Pending
M5095 | P1018 | Structural Work | 2026-02-17 |  | Not Started
M5096 | P1018 | Major Construction | 2026-06-01 |  | In Progress
M5097 | P1018 | Testing | 2026-09-13 | 2026-09-15 | Completed
M5098 | P1018 | Foundation | 2026-12-26 |  | Not Started
M5099 | P1019 | Design Approval | 2025-06-18 |  | In Progress
M5100 | P1019 | Major Construction | 2025-09-24 |  | In Progress
M5101 | P1019 | Land Acquisition | 2026-01-01 | 2026-01-11 | Delayed
M5102 | P1019 | Foundation | 2026-04-09 | 2026-04-14 | Delayed
M5103 | P1020 | N/A | 2024-05-22 | 2024-06-01 | Completed
M5104 | P1020 | Land Acquisition | 2024-07-23 |  | Pending
M5105 | P1020 | Structural Work | 2024-09-24 | 2024-11-23 | Completed
M5106 | P1020 | Foundation | 2024-11-25 | 2025-01-24
M5107 | P1020 | Design Approval | 2025-01-26 |  | Not Started
M5108 | P1021 | Structural Work | 2023-08-11 | 2023-08-16 | Completed
M5109 | P1021 | Design Approval | 2024-01-10 | 2024-01-30 | Completed
M5110 | P1021 | Foundation | 2024-06-09 | 2024-06-11 | N/A
M5111 | P1021 | Final Handover | 2024-11-08 | 2025-01-07 | Completed
M5112 | P1022 | Foundation | 2025-02-06 | 2025-04-07 | Completed
M5113 | P1022 | Land Acquisition | 2025-03-28 | 2025-05-27 | Completed
M5114 | P1022 | Final Handover | 2025-05-16 |  | Pending
M5115 | P1022 | Major Construction | 2025-07-05 | 2025-07-05 | Completed
M5116 | P1023 | Major Construction | 2025-08-06 | 2025-09-05 | Delayed
M5117 | P1023 | Foundation | 2025-10-21 | 2025-12-05 | Delayed
M5118 | P1023 | Structural Work | 2026-01-05 | 2026-01-25 | Delayed
M5119 | P1023 | Final Handover | 2026-03-22 | 2026-05-21 | Delayed
M5120 | P1023 | Testing | N/A | 2026-08-04 | Delayed
M5121 | P1024 | Foundation | N/A | 2022-04-03 | Completed
M5122 | P1024 | N/A | 2022-06-23 |  | Not Started
M5123 | P1024 | Final Handover | 2022-09-14 | 2022-09-16 | Completed
M5124 | P1024 | Land Acquisition | 2022-12-06 | 2023-02-24 | Delayed
M5125 | P1024 | Testing | 2023-02-27 | 2023-04-28 | Completed
M5126 | P1024 | Major Construction | 2023-05-21 | 2023-05-23 | Completed
M5127 | P1025 | Structural Work | 2024-07-12 |  | Not Started
M5128 | P1025 | Foundation | 2024-12-26 |  | In Progress
M5129 | P1025 | Major Construction | 2025-06-11 |  | In Progress
M5130 | P1025 | Safety Inspection | 2025-11-25 | 2025-11-27 | Delayed
M5131 | P1026 | Safety Inspection | 2025-11-15 |  | Not Started
M5132 | P1026 | Major Construction | 2026-01-03 | 2026-02-07 | Completed
M5133 | P1026 | Land Acquisition | 2026-02-21 | 2026-02-26 | Completed
M5134 | P1026 | Testing | 2026-04-12 |  | In Progress
M5135 | P1026 | Foundation | 2026-05-31 | 2026-07-05 | Completed
M5136 | P1026 | Structural Work | 2026-07-19 | 2026-08-08 | Completed
M5137 | P1027 | Safety Inspection | 2023-04-29 | 2023-07-16 | Delayed
M5138 | P1027 | Testing | 2023-08-23 |  | In Progress
M5139 | P1027 | Foundation | 2023-12-17 |  | In Progress
M5140 | P1027 | Design Approval | 2024-04-11 | 2024-04-11 | Completed
M5141 | P1028 | Structural Work | 2024-03-05 | 2024-03-07 | Completed
M5142 | P1028 | Testing | 2024-05-23 | 2024-06-02 | Completed
M5143 | P1028 | Major Construction | 2024-08-10 | 2024-09-17 | Delayed
M5144 | P1028 | Final Handover | 2024-10-28 |  | In Progress
M5145 | P1028 | Foundation | 2025-01-15 | 2025-02-27 | Delayed
M5146 | P1028 | Safety Inspection | 2025-04-04 | 2025-05-09 | Completed
M5147 | P1029 | Testing | 2025-01-29 | 2025-03-30 | Completed
M5148 | P1029 | Foundation | 2025-04-20 | 2025-04-22 | Completed
M5149 | P1029 | Safety Inspection | 2025-07-10
M5150 | P1029 | Major Construction | 2025-09-29 | 2025-10-09 | Completed
M5151 | P1029 | Final Handover | 2025-12-19 |  | Pending
M5152 | P1029 | Design Approval | 2026-03-10 | 2026-03-12 | Completed
M5153 | P1029 | Land Acquisition | 2026-05-30 | 2026-06-19 | Delayed
M5154 | P1030 | Testing | 2025-08-28 | 2025-10-02 | Completed
M5155 | P1030 | Safety Inspection | 2025-12-20 | 2025-12-20 | Completed
M5156 | P1030 | Final Handover | 2026-04-13 | 2026-04-15 | Completed
M5157 | P1030 | Design Approval | 2026-08-05 | 2026-08-07 | Delayed
M5158 | P1030 | Land Acquisition | 2026-11-27 | 2027-01-26 | N/A
M5159 | P1031 | Safety Inspection | 2022-05-12 |  | In Progress
M5160 | P1031 | Testing | 2022-09-18 | 2022-10-08 | Completed
M5161 | P1031 | Structural Work | 2023-01-25 |  | Pending
M5162 | P1031 | Final Handover | 2023-06-02 |  | Not Started
M5163 | P1031 | Major Construction | 2023-10-09 | 2023-11-13 | Completed
M5164 | P1032 | Structural Work | 2025-02-04 | 2025-02-24 | Completed
M5165 | P1032 | Testing | 2025-05-08 | 2025-07-07 | Completed
M5166 | P1032 | Foundation | 2025-08-09 | 2025-08-14 | Delayed
M5167 | P1032 | Safety Inspection | 2025-11-09 | 2026-01-06 | Delayed
M5168 | P1032 | Design Approval | N/A | 2026-03-17 | Completed
M5169 | P1033 | Final Handover | 2023-12-11 | 2024-01-15 | Completed
M5170 | P1033 | Foundation | 2024-03-14 | 2024-03-14 | Completed
M5171 | P1033 | Design Approval | 2024-06-15 | 2024-07-20 | Completed
M5172 | P1033 | Testing | 2024-09-17 | 2024-10-22 | Completed
M5173 | P1033 | Structural Work | 2024-12-19 |  | Not Started
M5174 | P1033 | Land Acquisition | 2025-03-23 | 2025-03-23 | Completed
M5175 | P1034 | Land Acquisition | 2025-04-05 | 2025-04-05 | Completed
M5176 | P1034 | Testing | 2025-08-28 | 2025-08-30
M5177 | P1034 | Final Handover | 2026-01-20 | 2026-02-05 | Delayed
M5178 | P1034 | Structural Work | 2026-06-14 | 2026-07-19 | Completed
M5179 | P1035 | Foundation | 2023-06-08 | 2023-06-08 | Delayed
M5180 | P1035 | Structural Work | 2023-08-10 | 2023-08-12 | Completed
M5181 | P1035 | Land Acquisition | 2023-10-12 | 2023-10-14 | Completed
M5182 | P1035 | Major Construction | 2023-12-15 | 2023-12-20 | N/A
M5183 | P1035 | Testing | 2024-02-16 | 2024-02-26 | Completed
M5184 | P1035 | Design Approval | 2024-04-19 | 2024-04-29 | Completed
M5185 | P1036 | Land Acquisition | 2024-06-29 |  | Not Started
M5186 | P1036 | Final Handover | 2024-10-31 | 2024-10-31 | Completed
M5187 | P1036 | Testing | 2025-03-05 |  | Pending
M5188 | P1036 | Safety Inspection | 2025-07-07 |  | Not Started
M5189 | P1036 | Major Construction | 2025-11-08 | 2025-11-13 | Completed
M5190 | P1037 | Land Acquisition | 2025-02-23 | 2025-02-23 | Completed
M5191 | P1037 | Final Handover | 2025-05-23 | 2025-05-23 | Completed
M5192 | P1037 | Design Approval | 2025-08-21 | 2025-09-25 | Completed
M5193 | P1037 | Safety Inspection | 2025-11-18 | 2025-11-28 | Completed
M5194 | P1037 | Foundation | 2026-02-15 | 2026-02-15 | Completed
M5195 | P1037 | Testing | 2026-05-16 | 2026-05-18 | Completed
M5196 | P1037 | Structural Work | 2026-08-13 | 2026-08-23 | Completed
M5197 | P1038 | Final Handover | 2025-01-22 |  | Pending
M5198 | P1038 | Safety Inspection | 2025-04-17 | 2025-05-07 | Delayed
M5199 | P1038 | Structural Work | 2025-07-10 |  | Not Started
M5200 | P1038 | Design Approval | 2025-10-03 | 2025-10-23 | Delayed
M5201 | P1038 | Land Acquisition | 2025-12-26 | 2026-01-13 | Delayed
M5202 | P1038 | Testing | 2026-03-21 |  | Not Started
M5203 | P1038 | Foundation | 2026-06-13 |  | Pending
M5204 |  | Final Handover | 2025-09-05 | 2025-09-05 | Completed
M5205 | P1039 | Land Acquisition | 2025-11-05 | 2025-12-10 | Completed
M5206 | P1039 | Structural Work | 2026-01-04 | 2026-02-08 | Completed
M5207 | P1039 | Testing | 2026-03-06 | 2026-04-10 | Completed
M5208 | P1039 | Safety Inspection | 2026-05-05 | 2026-06-09 | Delayed
M5209 | P1039 | Major Construction | 2026-07-05 | 2026-09-03 | Completed
M5210 | P1039 | N/A | 2026-09-03 | 2026-09-05 | Delayed
M5211 | P1040 | Foundation | N/A | 2026-01-12 | Delayed
M5212 | P1040 | Land Acquisition | 2026-03-01 | 2026-03-03 | Completed
M5213 | P1040 | Structural Work | 2026-04-19 | 2026-06-18 | Delayed
M5214 | P1040 | Final Handover | 2026-06-08 | 2026-06-18 | Delayed
M5215 | P1040 | Design Approval | 2026-07-27 | 2026-08-06 | Completed
M5216 | P1040 | Testing | 2026-09-15 |  | Completed
M5217 | P1040 | Major Construction | 2026-11-03 | 2026-11-18 | Delayed
M5218 | P1041 | Major Construction | 2024-10-22 |  | In Progress
M5219 | P1041 | Final Handover | 2024-12-10 |  | In Progress
M5220 | P1041 | Safety Inspection | N/A |  | Pending
M5221 | P1041 | Design Approval | 2025-03-18 |  | In Progress
M5222 | P1042 | Testing | 2023-10-06 | 2023-10-11 | Completed
M5223 | P1042 | Final Handover | 2023-12-31 | 2024-01-05 | Completed
M5224 | P1042 | Structural Work | 2024-03-26 | 2024-03-28 | Delayed
M5225 | P1042 | Land Acquisition | 2024-06-20 | 2024-07-25 | Delayed
M5226 | P1042 | Major Construction | 2024-09-13 | 2024-10-03 | Completed
M5227 | P1042 | Foundation | 2024-12-08 | 2025-02-06 | Delayed
M5228 | P1042 | Safety Inspection | 2025-03-04 | 2025-05-03 | Completed
M5229 | P1043 | Design Approval | 2025-07-10 | 2025-07-30 | Completed
M5230 | P1043 | Safety Inspection | 2025-11-18 | 2025-11-18 | Completed
M5231 | P1043 | Structural Work | 2026-03-29 | 2026-04-08 | Delayed
M5232 | P1043 | Land Acquisition | 2026-08-07 | 2026-10-06 | Completed
M5233 | P1043 | Major Construction | 2026-12-16 | 2026-12-18 | Completed
M5234 | P1043 | Final Handover | 2027-04-26 | 2027-05-31 | Completed
M5235 | P1044 | Safety Inspection | 2023-10-15 | 2023-10-25 | Completed
M5236 | P1044 | Major Construction | 2024-01-07 | 2024-01-27 | Completed
M5237 | P1044 | Testing | 2024-03-31 | 2024-04-20 | Completed
M5238 | P1044 | Design Approval | 2024-06-23 | 2024-07-13 | Completed
M5239 | P1044 | Foundation | 2024-09-15 | 2024-10-05 | Completed
M5240 | P1044 | Final Handover | 2024-12-08 | 2025-01-12 | Completed
M5241 | P1044 | Structural Work | 2025-03-02 | 2025-04-06 | Completed
M5242 | P1045 | Design Approval | 2022-05-14 | 2022-06-18 | Delayed
M5243 | P1045 | Safety Inspection | 2022-07-23 | 2022-09-21 | Completed
M5244 | P1045 |  | 2022-10-02 | 2022-10-12 | Completed
M5245 | P1045 | Major Construction | 2022-12-11 | 2022-12-11 | Delayed
M5246 | P1045 | Structural Work | 2023-02-20 | 2023-03-27 | Completed
M5247 | P1045 |  | 2023-05-01 | 2023-06-30 | Completed
M5248 | P1046 | Major Construction | 2024-03-24 | 2024-05-23 | Delayed
M5249 | N/A | Design Approval | 2024-05-22 | 2024-07-21 | Completed
M5250 | P1046 | Land Acquisition | 2024-07-20 |  | Not Started
M5251 | P1046 | Foundation | 2024-09-16 | 2024-10-06 | Completed
M5252 | P1046 | Safety Inspection |  |  | Pending
M5253 | P1046 | Final Handover | 2025-01-12 |  | In Progress
M5254 | P1047 | Testing | 2023-03-22 |  | Not Started
M5255 | P1047 | Major Construction | 2023-05-01 |  | Not Started
M5256 | P1047 | Land Acquisition | 2023-06-09 | 2023-06-29 | Completed
M5257 | P1047 | Final Handover | 2023-07-19 |  | Pending
M5258 | P1047 | Foundation | 2023-08-28 | 2023-08-30 | Completed
M5259 | P1047 | Safety Inspection | 2023-10-06 | 2023-10-08 | Completed
M5260 | P1047 | Design Approval | 2023-11-15 | 2023-11-25 | Completed
M5261 | P1048 | Foundation | 2024-10-05 | 2024-10-07 | Completed
M5262 | P1048 | Design Approval | 2025-02-13 | 2025-02-18 | Completed
M5263 | P1048 | Major Construction | 2025-06-24 |  | Not Started
M5264 | P1048 | Final Handover | 2025-11-02 |  | Not Started
M5265 | P1048 | Land Acquisition | 2026-03-13 | 2026-05-12 | Completed
M5266 | P1048 | Safety Inspection | 2026-07-22 | 2026-08-26 | Completed
M5267 | P1049 | Foundation | 2024-08-19 | 2024-09-08 | Delayed
M5268 | P1049 | Major Construction | 2024-10-28 | 2024-10-30 | Completed
M5269 | P1049 | Land Acquisition | 2025-01-06 | 2025-03-04 | Delayed
M5270 | P1049 | Safety Inspection | 2025-03-17 | 2025-03-19 | Delayed
M5271 | P1049 | Design Approval | 2025-05-26 |  | Not Started
M5272 | P1050 | Design Approval | 2022-10-10 | 2022-11-14 | Completed
M5273 | P1050 | Testing | 2023-01-23 |  | Not Started
M5274 | P1050 | Foundation | 2023-05-08 |  | In Progress
M5275 | P1050 | Structural Work | 2023-08-21 |  | Pending
M5276 | P1051 | Major Construction | 2024-02-29 | 2024-03-20 | Delayed
M5277 | P1051 | Final Handover | 2024-05-02 | 2024-05-07 | Completed
M5278 | P1051 | Testing | 2024-07-04 | 2024-07-04 | Completed
M5279 | P1051 | Foundation | 2024-09-05 | 2024-11-04 | Completed
M5280 | P1051 | Land Acquisition | 2024-11-07 | 2024-11-09 | Completed
M5281 | P1051 | Safety Inspection | 2025-01-09 | 2025-01-19 | Completed
M5282 | P1051 | Design Approval | 2025-03-13 | 2025-05-12 | Delayed
M5283 | P1052 | Foundation | 2026-01-10 | 2026-01-10 | Completed
M5284 | P1052 | Land Acquisition | 2026-06-07 | 2026-06-12 | Completed
M5285 | P1052 | Structural Work | 2026-11-03 |  | Pending
M5286 | P1052 | Final Handover | 2027-03-31 |  | In Progress
M5287 | P1053 | Final Handover | 2025-04-14 |  | Not Started
M5288 | P1053 | Testing | 2025-06-25 | 2025-07-30 | Completed
M5289 | P1053 | Structural Work | 2025-09-05 |  | Not Started
M5290 | P1053 | Safety Inspection | 2025-11-17 | 2026-01-16 | Completed
M5291 | P1053 | Foundation | 2026-01-28 | 2026-02-17 | Completed
M5292 | P1053 |  | 2026-04-10 | 2026-05-15 | Completed
M5293 | P1053 | Design Approval | 2026-06-21 |  | In Progress
M5294 | P1054 | Safety Inspection | 2024-11-22 | 2024-12-02 | Completed
M5295 | P1054 | Structural Work | 2025-01-26 |  | Pending
M5296 | N/A | Testing | 2025-04-02 | 2025-06-01 | Completed
M5297 | P1054 | Land Acquisition | 2025-06-06 |  | Pending
M5298 | P1054 | Final Handover | 2025-08-10 | 2025-09-12 | Delayed
M5299 | P1054 | Major Construction | 2025-10-15 | 2025-10-15 | Delayed
M5300 | P1054 | Foundation | 2025-12-19 | 2025-12-19 | Completed
M5301 | P1055 | Testing | 2025-02-28 | 2025-03-02 | Completed
M5302 | P1055 | Design Approval | 2025-05-01 | 2025-05-03 | Completed
M5303 | P1055 | Structural Work | 2025-07-01 | 2025-07-21 | Delayed
M5304 | P1055 | Major Construction | 2025-09-01 | 2025-09-01 | Completed
M5305 | P1055 | Safety Inspection | 2025-11-01 | 2025-11-06 | Completed
M5306 | P1056 | Final Handover | 2024-12-18 | 2025-01-07 | Completed
M5307 | P1056 | Foundation | 2025-04-19 |  | In Progress
M5308 | P1056 | Safety Inspection | 2025-08-19 | 2025-08-24 | Completed
M5309 | P1056 | Design Approval | 2025-12-18 |  | Pending
M5310 | N/A | Major Construction | 2026-04-19 |  | In Progress
M5311 | P1057 | Safety Inspection | 2025-12-18 | 2026-01-22 | Delayed
M5312 | P1057 | Design Approval | 2026-01-29 | 2026-02-03 | Completed
M5313 | P1057 | Land Acquisition | 2026-03-12 | 2026-03-17 | Delayed
M5314 | P1057 | Foundation | 2026-04-23 | 2026-04-28 | Completed
M5315 | P1057 | Final Handover | 2026-06-04 | 2026-06-04 | Completed
M5316 | P1057 | Testing | 2026-07-16 | 2026-07-16 | Completed
M5317 | P1058 | Structural Work | 2024-11-03 | 2025-01-02 | Completed
M5318 | P1058 | Foundation | 2025-02-27 | 2025-03-19 | Delayed
M5319 | P1058 | Testing | 2025-06-22 | 2025-06-24 | Completed
M5320 | P1058 | Land Acquisition | 2025-10-16 | 2025-11-05 | Delayed
M5321 | P1058 | Major Construction | 2026-02-08 | 2026-02-10 | Completed
M5322 | P1059 | Structural Work | 2023-10-18 | 2023-11-07 | Completed
M5323 | P1059 | Safety Inspection | 2024-02-10 | 2024-04-10 | Completed
M5324 | P1059 | Major Construction | 2024-06-03 | 2024-06-05 | Delayed
M5325 | P1059 | Foundation | 2024-09-26 | 2024-10-16 | Completed
M5326 | P1059 | Design Approval | 2025-01-18 | 2025-01-28 | Completed
M5327 | P1059 | Final Handover | 2025-05-13 | 2025-07-12 | Delayed
M5328 | P1059 | Land Acquisition | 2025-09-04 | 2025-09-09 | Completed
M5329 | P1060 | Land Acquisition | 2023-11-10 | 2023-11-20 | Completed
M5330 | P1060 | Testing | 2024-02-06 | 2024-03-12 | Completed
M5331 | P1060 | Design Approval | 2024-05-04 | 2024-05-24 | Completed
M5332 | P1060 | Major Construction | 2024-07-31 |  | In Progress
M5333 | P1060 | Foundation | 2024-10-27 | 2024-12-03 | Delayed
M5334 | P1061 | Safety Inspection | 2025-03-19 | 2025-03-24 | Completed
M5335 | P1061 | Foundation | 2025-05-17 | 2025-05-27 | Completed
M5336 | P1061 | Major Construction | 2025-07-15 | 2025-07-17 | Delayed
M5337 | P1061 | Land Acquisition | 2025-09-12 | 2025-09-12 | Completed
M5338 | P1061 | Final Handover | 2025-11-09 | 2025-11-11 | Completed
M5339 | P1061 | Design Approval | 2026-01-07 | 2026-02-11 | Completed
M5340 | P1061 | Testing | 2026-03-07 |  | In Progress
M5341 | P1062 | Design Approval | 2024-12-30 | 2025-02-03 | Delayed
M5342 | P1062 | Structural Work | 2025-05-14 | 2025-05-14 | Completed
M5343 | P1062 | Testing | 2025-09-26 | 2025-09-28 | N/A
M5344 | P1062 | Safety Inspection | 2026-02-08 | 2026-02-08 | Completed
M5345 | P1062 | Major Construction | 2026-06-23 | 2026-06-28 | Completed
M5346 | P1062 | Land Acquisition | 2026-11-05 | 2026-11-15 | Completed
M5347 | P1063 | Design Approval | 2025-07-30 | 2025-09-28 | Delayed
M5348 | P1063 | Final Handover | 2025-10-09 | 2025-12-08 | Completed
M5349 | P1063 | Structural Work | 2025-12-19 | 2026-01-08 | Completed
M5350 | P1063 | Major Construction | 2026-02-28 | 2026-04-04 | Completed
M5351 | P1063 | Testing | 2026-05-10 | 2026-05-30 | Completed
M5352 | P1063 | Safety Inspection | 2026-07-20 | 2026-07-30 | Completed
M5353 | P1064 | Land Acquisition | 2023-05-18 |  | Pending
M5354 | P1064 | Design Approval | 2023-10-09 |  | Pending
M5355 | P1064 | Major Construction | 2024-03-01 | 2024-03-21 | Completed
M5356 | P1064 | Testing | 2024-07-23 |  | Not Started
M5357 | P1065 | Design Approval | 2024-03-06 |  | Not Started
M5358 | P1065 | Structural Work | 2024-06-28 |  | Not Started
M5359 | P1065 | Testing | 2024-10-19 | 2024-12-26 | Delayed
M5360 | P1065 | Final Handover | 2025-02-10 | 2025-02-10 | Delayed
M5361 | P1066 | Final Handover | 2023-12-29 | 2024-01-03 | Delayed
M5362 | P1066 | Safety Inspection | 2024-03-21 | 2024-05-20 | Completed
M5363 | P1066 | Structural Work | 2024-06-12 | 2024-07-02 | Delayed
M5364 | P1066 | Foundation | 2024-09-03 | 2024-09-03 | Completed
M5365 | P1066 | Land Acquisition | 2024-11-25 | 2024-11-25 | Completed
M5366 | P1067 |  | 2024-04-29 | 2024-05-19 | Completed
M5367 | P1067 | Testing | 2024-08-17 | 2024-09-06 | Delayed
M5368 | P1067 | Foundation | 2024-12-04 | 2025-01-23 | Delayed
M5369 | P1067 | Final Handover | 2025-03-24 |  | In Progress
M5370 | P1067 | Safety Inspection | 2025-07-12 | 2025-09-17 | Delayed
M5371 | P1067 | Land Acquisition | 2025-10-29 | 2026-01-13 | Delayed
M5372 | P1067 | Major Construction | 2026-02-16 | 2026-03-08 | Delayed
M5373 | P1068 | Major Construction | 2025-11-14 | 2025-11-16 | Delayed
M5374 | P1068 | Final Handover | 2026-03-17 | 2026-04-21 | Delayed
M5375 | P1068 | Foundation | 2026-07-18 | 2026-08-07 | Delayed
M5376 | P1068 | Structural Work | 2026-11-19 | 2026-12-10 | Delayed
M5377 | P1068 | Design Approval | 2027-03-22 | 2027-04-26 | Completed
M5378 | P1068 | Testing | 2027-07-23 |  | Pending
M5379 | P1069 | Safety Inspection | 2025-10-07 |  | Not Started
M5380 | P1069 | Land Acquisition | 2025-11-26 | 2025-12-06 | Completed
M5381 | P1069 | Final Handover | 2026-01-14 |  | Not Started
M5382 | P1069 | Foundation | 2026-03-05 | 2026-05-04 | Completed
M5383 | P1069 | Design Approval | 2026-04-24 |  | In Progress
M5384 | P1069 | Structural Work | 2026-06-12 | 2026-08-11 | Completed
M5385 | P1069 | Testing | 2026-08-01 | 2026-09-30 | Completed
M5386 | P1070 | Land Acquisition | 2025-09-15 | 2025-09-20 | Delayed
M5387 | P1070 | Foundation | 2026-01-20 | 2026-01-30 | Delayed
M5388 | P1070 | Design Approval | 2026-05-27 | 2026-06-12 | Delayed
M5389 | P1070 | Final Handover | 2026-09-30 | 2026-10-23 | Delayed
M5390 | P1070 | Testing | 2027-02-04 |  | Not Started
M5391 | P1071 | Testing | 2024-01-02 |  | Not Started
M5392 | P1071 | Foundation | 2024-05-01 | 2024-05-03 | Delayed
M5393 | P1071 | Safety Inspection | 2024-08-29 | 2024-09-18 | Completed
M5394 | P1071 | Design Approval | 2024-12-27 | 2025-01-01 | Completed
M5395 | P1071 | Major Construction | 2025-04-26 |  | In Progress
M5396 | P1071 | Structural Work | 2025-08-24 |  | Not Started
M5397 | P1072 | Final Handover | 2026-02-06 | N/A | In Progress
M5398 | P1072 | Structural Work | 2026-04-16 |  | Not Started
M5399 | p1072 | Major Construction | 2026-06-24 |  | In Progress
M5400 | P1072 | Safety Inspection | 2026-09-01 | 2026-09-01 | Delayed
M5401 | P1072 | Design Approval | 2026-11-09 |  | Pending
M5402 | P1072 | Testing | 2027-01-17 |  | Pending
M5403 | P1073 | Safety Inspection | 2023-02-22 |  | Pending
M5404 | P1073 | Foundation | 2023-06-09 | 2023-06-19 | Completed
M5405 | P1073 | Major Construction | 2023-09-24 | 2023-09-26 | Delayed
M5406 | P1073 | Testing | 2024-01-08 | 2024-01-10 | Completed
M5407 | P1073 | Land Acquisition | 2024-04-24 | 2024-05-29
M5408 | P1073 | Final Handover | 2024-08-09 | 2024-08-11 | Completed
M5409 | P1074 | Major Construction | 2023-02-09 |  | In Progress
M5410 | P1074 | Design Approval | 2023-05-30 | 2023-05-30 | Completed
M5411 | P1074 | N/A | 2023-09-17 |  | Not Started
M5412 | P1074 | Testing | 2024-01-05 |  | In Progress
M5413 | P1074 | Final Handover | 2024-04-24 |  | Not Started
M5414 | P1075 | Final Handover | 2024-06-09 | 2024-06-29 | Completed
M5415 | P1075 | Foundation | 2024-09-30 | 2024-11-29 | Completed
M5416 | P1075 | Major Construction | 2025-01-21 | 2025-03-22 | Completed
M5417 | P1075 | Safety Inspection | 2025-05-14 | 2025-07-13 | Delayed
M5418 | P1076 | Land Acquisition | 2025-09-01 |  | In Progress
M5419 | P1076 | Major Construction | 2025-10-14 | 2025-10-14 | Completed
M5420 | P1076 | Foundation | 2025-11-26 |  | In Progress
M5421 | P1076 | Structural Work | 2026-01-08 |  | In Progress
M5422 | P1076 | Design Approval | 2026-02-19 | 2026-04-20 | Completed
M5423 | P1076 | Safety Inspection | 2026-04-03 | 2026-04-08 | N/A
M5424 | P1076 | Final Handover | 2026-05-16 | 2026-06-05 | Completed
M5425 | P1077 | Foundation | 2025-07-17 | 2025-09-16 | Delayed
M5426 | P1077 | Structural Work | 2025-11-28 |  | In Progress
M5427 | P1077 | Safety Inspection | 2026-04-11 | 2026-05-01 | Completed
M5428 | P1077 | Design Approval | 2026-08-23 |  | Not Started
M5429 | P1077 | Testing | 2027-01-04 | 2027-01-04 | Completed
M5430 | N/A | Final Handover | 2027-05-18 |  | Not Started
M5431 | P1078 | Safety Inspection | 2025-09-30 | 2025-10-02 | Completed
M5432 | P1078 | Design Approval | 2025-12-02 |  | In Progress
M5433 | P1078 | Final Handover | 2026-02-02 | 2026-04-03 | Completed
M5434 | P1078 | Testing | 2026-04-06 | 2026-05-11 | Completed
M5435 | P1078 | Structural Work | 2026-06-07 | 2026-08-06 | Completed
M5436 | P1078 | Land Acquisition | 2026-08-09 | 2026-09-13 | Completed
M5437 | P1078 | Foundation | 2026-10-10 | 2026-10-15 | Completed
M5438 | P1079 | Testing | 2026-01-23 | 2026-01-28 | Completed
M5439 | P1079 | Major Construction | 2026-04-04 |  | Not Started
M5440 | P1079 | Safety Inspection | 2026-06-14 |  | Pending
M5441 | P1079 | Foundation | 2026-08-24 |  | In Progress
M5442 | P1079 | Final Handover | 2026-11-03 | 2026-12-08 | Delayed
M5443 | P1079 | Land Acquisition | 2027-01-13 |  | In Progress
M5444 | P1080 | Safety Inspection | 2022-08-15 |  | Pending
M5445 | P1080 | Major Construction | 2023-02-14 |  | Not Started
M5446 | P1080 | Foundation | 2023-08-16 |  | In Progress
M5447 | P1080 | Structural Work | 2024-02-15 | 2024-03-06 | Delayed
M5448 | P1081 | Design Approval | 2024-03-24 | 2024-04-28 | Completed
M5449 | P1081 | Final Handover | 2024-06-25 |  | Not Started
M5450 | P1081 | Foundation | 2024-09-26 |  | In Progress
M5451 | P1081 | Safety Inspection | 2024-12-28 |  | In Progress
M5452 | P1082 | Safety Inspection | 2022-06-22 |  | Not Started
M5453 | P1082 | Design Approval | 2022-10-04 |  | Pending
M5454 | P1082 | Final Handover | 2023-01-16 | 2023-01-26 | Completed
M5455 | P1082 | Land Acquisition | 2023-04-30 | 2023-05-10 | Completed
M5456 | P1082 | Testing | 2023-08-12 | 2023-08-22 | Completed
M5457 | P1082 | Foundation | 2023-11-24 | 2023-12-14 | Completed
M5458 | P1082 | Major Construction | 2024-03-07 | 2024-03-17 | Completed
M5459 | P1083 | Structural Work | 2023-09-19 | 2023-11-18 | Completed
M5460 | P1083 | Testing | 2023-11-26 | N/A | Completed
M5461 | P1083 | Foundation | 2024-02-02 | 2024-02-07 | Delayed
M5462 | P1083 | Final Handover | 2024-04-10 | 2024-06-09 | Completed
M5463 | P1083 | Design Approval | 2024-06-17 | 2024-06-19 | Completed
M5464 | P1084 | Safety Inspection | 2026-02-10 | 2026-04-11 | Completed
M5465 | P1084 | Major Construction | 2026-06-06 | 2026-06-11 | Delayed
M5466 | P1084 | Testing | 2026-09-30 | 2026-10-05 | Completed
M5467 | P1084 | Final Handover | 2027-01-25 | 2027-03-26 | Completed
M5468 | P1084 | Foundation | 2027-05-21 | 2027-05-31 | Completed
M5469 | P1084 | Design Approval | 2027-09-14 |  | In Progress
M5470 | P1084 | Structural Work | 2028-01-08 |  | In Progress
M5471 | P1085 | Land Acquisition | 2025-10-27 | 2025-10-29 | Delayed
M5472 | P1085 | Safety Inspection | 2026-01-24 | 2026-02-03 | Delayed
M5473 |  | Structural Work | 2026-04-22 | 2026-05-27 | Delayed
M5474 | P1085 | Foundation | 2026-07-20 | 2026-07-22 | Completed
M5475 | P1085 | Design Approval | 2026-10-16 | 2026-11-20 | Completed
M5476 | P1085 | Final Handover | 2027-01-13 | N/A | Completed
M5477 | P1086 | Major Construction | 2026-02-22 | 2026-03-29 | Delayed
M5478 | P1086 | Structural Work | 2026-05-11 |  | In Progress
M5479 | P1086 | Design Approval | 2026-07-29 |  | In Progress
M5480 | P1086 | Land Acquisition | 2026-10-15 | 2026-10-15 | Completed
M5481 | P1086 | Testing | 2027-01-02 | 2027-01-22 | Completed
M5482 | P1086 | Final Handover | 2027-03-21 | 2027-03-21 | Completed
M5483 | P1087 | Foundation | 2024-06-10 | 2024-06-20 | Completed
M5484 | P1087 | Testing | 2024-10-20 | 2024-10-25 | Delayed
M5485 | P1087 | Structural Work | 2025-03-01 |  | In Progress
M5486 | P1087 | Land Acquisition | 2025-07-12 |  | Pending
M5487 | P1087 | Design Approval | 2025-11-21 | 2026-01-20 | Completed
M5488 | P1087 | Major Construction | 2026-04-02 | 2026-06-01 | Delayed
M5489 | P1088 | Final Handover | 2026-03-17 | N/A | Completed
M5490 | P1088 | Design Approval | 2026-07-19 | 2026-09-17 | Completed
M5491 | P1088 | Safety Inspection | 2026-11-20 | 2026-11-30 | Completed
M5492 | P1088 | Foundation | 2027-03-24 | 2027-03-24 | Completed
M5493 | P1089 |  | 2023-09-12 |  | Pending
M5494 | P1089 | Major Construction | 2023-11-05 |  | Pending
M5495 | P1089 | Testing | 2023-12-29 |  | Not Started
M5496 | P1089 | Final Handover | 2024-02-22 | 2024-02-27 | Delayed
M5497 | P1089 | Structural Work | 2024-04-16 |  | Pending
M5498 | P1089 | Safety Inspection | 2024-06-09 | 2024-06-09 | Completed
M5499 | P1089 | Foundation | 2024-08-02 |  | Pending
M5500 | P1090 | Testing | 2023-04-04 | 2023-04-04 | Delayed
M5501 | P1090 | Land Acquisition | 2023-05-13 | 2023-06-16 | Delayed
M5502 | P1090 | Design Approval | 2023-06-21 | 2023-06-21 | Completed
M5503 | P1090 | Foundation | 2023-07-30 | 2023-07-30 | Completed
M5504 | P1090 | Safety Inspection | 2023-09-06 |  | Not Started
M5505 | P1090 | Final Handover | 2023-10-15 | 2023-10-20 | Completed
M5506 | P1090 | Structural Work | 2023-11-23 | 2023-12-21 | Delayed
M5507 | P1091 | Final Handover | 2023-02-03 | 2023-02-13 | Completed
M5508 | P1091 | Design Approval | 2023-06-15 | 2023-06-25 | Completed
M5509 | P1091 | Foundation | 2023-10-25 | 2023-10-30 | Completed
M5510 | P1091 | Major Construction | 2024-03-05 | 2024-03-15 | Completed
M5511 | P1091 | Testing | 2024-07-15 | 2024-07-25 | Completed
M5512 | P1092 | Testing | 2023-08-15 | 2023-09-04 | Completed
M5513 | P1092 | Foundation | 2023-10-03 | 2023-10-05 | Delayed
M5514 | P1092 | Final Handover | 2023-11-21 | 2023-11-26 | Completed
M5515 | P1092 | Structural Work | 2024-01-09 | 2024-03-09 | Delayed
M5516 | P1092 | Safety Inspection | 2024-02-27 | 2024-02-27 | Completed
M5517 | P1093 | Testing | 2023-08-21 | 2023-09-25 | Delayed
M5518 | P1093 | Final Handover | 2024-01-13 | 2024-01-15 | Completed
M5519 | P1093 | Land Acquisition | 2024-06-06 | 2024-07-11 | Completed
M5520 | P1093 | Major Construction | 2024-10-29 | 2024-11-18 | Completed
M5521 | P1093 | Structural Work | 2025-03-23 | 2025-03-25 | Completed
M5522 | P1094 | Structural Work | 2024-08-29 | 2024-09-18 | N/A
M5523 | P1094 | Land Acquisition | 2024-10-31 |  | Not Started
M5524 |  | Final Handover | 2025-01-02 |  | Not Started
M5525 | P1094 | Design Approval | 2025-03-06 | 2025-03-11 | Completed
M5526 | P1095 | Land Acquisition | 2024-01-14 |  | Pending
M5527 | P1095 | Design Approval | 2024-06-03 | 2024-07-08 | Completed
M5528 | P1095 | Testing | 2024-10-22 | 2024-11-26 | Delayed
M5529 | P1095 | Structural Work | 2025-03-12 |  | Not Started
M5530 | P1096 | Major Construction | 2023-08-23 | 2023-08-23 | Completed
M5531 | P1096 | Final Handover | 2024-01-03 | 2024-01-03 | Completed
M5532 | P1096 | Land Acquisition | 2024-05-14 | 2024-06-03 | Delayed
M5533 | P1096 | Testing | 2024-09-24 | 2024-10-14 | Completed
M5534 | P1097 | Safety Inspection | 2022-07-12 | 2022-09-19 | Delayed
M5535 | P1097 | Testing | N/A |  | Pending
M5536 | P1097 | Land Acquisition | 2022-10-31 | 2023-01-05 | Delayed
M5537 | P1097 | Major Construction | 2022-12-26 | 2023-01-30 | Completed
M5538 | P1097 | Foundation | 2023-02-19 | 2023-03-11 | Delayed
M5539 | P1098 | Testing | 2024-07-16 | 2024-08-20 | Completed
M5540 | P1098 | Major Construction | 2024-10-10 |  | Not Started
M5541 | P1098 | Foundation | 2025-01-04 | 2025-01-14 | Completed
M5542 | P1098 | Final Handover | 2025-03-31 | 2025-04-10 | Delayed
M5543 | P1098 | Structural Work | 2025-06-25 |  | Pending
M5544 | P1098 | Safety Inspection | 2025-09-19 |  | In Progress
M5545 | P1099 | Foundation | 2023-05-30 |  | Pending
M5546 | P1099 | Final Handover | 2023-08-18 |  | Pending
M5547 | P1099 | Land Acquisition | 2023-11-05 | 2023-12-25 | Delayed
M5548 | P1099 | Safety Inspection | 2024-01-24 |  | Not Started
M5549 | P1100 | Design Approval | 2025-11-12 | 2025-11-17 | Completed
M5550 | P1100 | Land Acquisition | 2026-04-16 | 2026-06-15 | Completed
M5551 | P1100 | Structural Work | 2026-09-18 | 2026-09-28 | Completed
M5552 | P1100 | Foundation | 2027-02-20 |  | Not Started
M5553 | P1100 | Final Handover | 2027-07-25 | 2027-08-04 | Completed
M5554 | P1101 | Design Approval | 2022-03-07 | 2022-03-07 | Completed
M5555 | P1101 | Major Construction | 2022-04-29 | 2022-06-28 | Delayed
M5556 | P1101 | Testing | 2022-06-21 | 2022-08-20 | Completed
M5557 | P1101 | Foundation | 2022-08-13 |  | Pending
M5558 | P1101 | Land Acquisition | 2022-10-05 |  | Not Started
M5559 | P1101 | Safety Inspection | 2022-11-27 |  | Not Started
M5560 | P1101 | Final Handover | 2023-01-19 |  | In Progress
M5561 | P1102 | Major Construction | 2024-11-12 | 2024-11-14 | Completed
M5562 | P1102 | Final Handover | 2025-03-10 | 2025-03-12 | Completed
M5563 | P1102 | Land Acquisition | 2025-07-06 | 2025-08-10 | Delayed
M5564 | P1102 | Foundation | 2025-11-01 | 2025-12-31 | Completed
M5565 | P1103 | Safety Inspection | 2025-12-04 | 2025-12-14 | Completed
M5566 | P1103 | Foundation | 2026-01-27 | 2026-02-01 | Completed
M5567 | P1103 | Structural Work | 2026-03-22 | 2026-04-01 | Completed
M5568 | P1103 | Design Approval | 2026-05-15 | 2026-05-25 | Completed
M5569 | P1103 | Major Construction | 2026-07-08 | 2026-08-12 | Completed
M5570 | P1104 | Structural Work | 2026-03-24 |  | Not Started
M5571 | P1104 | Land Acquisition | 2026-08-27 | 2026-10-01 | Delayed
M5572 | P1104 | Foundation | 2027-01-30 | 2027-02-04 | Completed
M5573 | P1104 | Final Handover | 2027-07-04 | 2027-07-24 | Completed
M5574 | P1104 | Testing | 2027-12-07 |  | Pending
M5575 | P1105 | Final Handover | 2023-12-24 | 2023-12-29 | Completed
M5576 | P1105 | Major Construction | 2024-02-14 | 2024-04-14 | Completed
M5577 | P1105 | Design Approval | 2024-04-06 | 2024-04-06 | Completed
M5578 | P1105 | Structural Work | 2024-05-27 | 2024-05-29 | Completed
M5579 | P1105 | Land Acquisition | 2024-07-18 | 2024-08-22 | Completed
M5580 | P1105 | Safety Inspection | 2024-09-08 | 2024-09-18 | Completed
M5581 | P1106 | Structural Work | 2022-07-04 |  | Delayed
M5582 | P1106 | Testing | 2022-10-10 | 2022-10-12 | Completed
M5583 | P1106 | Major Construction | 2023-01-16 | 2023-02-20 | Completed
M5584 | P1106 | Design Approval | 2023-04-24 | 2023-04-24 | Completed
M5585 | P1106 | Safety Inspection | 2023-07-31 | 2023-09-04 | Completed
M5586 | P1106 | Foundation | 2023-11-06 | 2023-12-11 | Completed
M5587 | P1107 | Safety Inspection | 2024-01-19 |  | Pending
M5588 | N/A | Testing | 2024-04-11 | 2024-05-16 | Delayed
M5589 | P1107 | Foundation | 2024-07-03 | 2024-07-13 | Completed
M5590 | P1107 | Final Handover | 2024-09-24 |  | In Progress
M5591 | P1108 | Foundation | 2024-07-10 | 2024-07-27 | Delayed
M5592 | N/A | Design Approval | 2024-10-29 | 2024-11-18 | Completed
M5593 | P1108 | Major Construction | 2025-02-18 | 2025-02-28 | Completed
M5594 | P1108 | Structural Work | 2025-06-09 | 2025-07-14 | Completed
M5595 | P1109 | Major Construction | 2025-10-08 | 2025-10-18 | Completed
M5596 | P1109 | Design Approval | 2025-12-03 | 2025-12-08 | Completed
M5597 | P1109 | Final Handover | 2026-01-28 | 2026-02-07 | Completed
M5598 | P1109 | Foundation | 2026-03-25 | 2026-04-04 | Completed
M5599 | P1109 | Land Acquisition | 2026-05-20 | 2026-06-09 | Completed
M5600 | P1109 | Testing | 2026-07-15 | 2026-07-20 | Completed
M5601 | P1110 | Foundation | 2025-06-27 | 2025-07-29 | Delayed
M5602 | P1110 | Design Approval | 2025-09-22 | 2025-11-21 | Completed
M5603 | P1110 | Testing | 2025-12-19 | 2026-01-23 | Delayed
M5604 | P1110 | Safety Inspection | 2026-03-16 | 2026-04-05 | Completed
M5605 | P1110 | Major Construction | 2026-06-11 | 2026-08-10 | Completed
M5606 | P1110 | Land Acquisition | 2026-09-07 | 2026-11-01 | Delayed
M5607 | P1110 | Structural Work | 2026-12-03 |  | In Progress
M5608 | P1111 | Major Construction | 2025-09-23 | 2025-09-23 | Completed
M5609 | P1111 | Structural Work | 2025-12-01 | 2026-01-14 | Delayed
M5610 | P1111 | Testing | 2026-02-08 | 2026-03-24 | Delayed
M5611 | P1111 | Foundation | 2026-04-18 | 2026-06-17 | Delayed
M5612 | P1111 | Design Approval | 2026-06-25 | 2026-08-24 | Delayed
M5613 | P1111 | Land Acquisition | 2026-09-02 | 2026-11-01 | Delayed
M5614 | P1111 | Final Handover | 2026-11-10 | 2027-01-11 | Delayed
M5615 | p1112 | Safety Inspection | 2022-11-25 | 2022-11-25 | Delayed
M5616 | P1112 | Structural Work | 2023-04-19 |  | Pending
M5617 | P1112 | Final Handover | 2023-09-11 |  | In Progress
M5618 | P1112 | Design Approval | 2024-02-03 | 2024-03-09 | Completed
M5619 | P1112 | Major Construction | 2024-06-27 |  | Pending
M5620 | P1113 | Final Handover | 2025-01-04 | 2025-01-06 | Delayed
M5621 | P1113 | Safety Inspection | 2025-05-10 | 2025-05-10 | Delayed
M5622 | P1113 | Major Construction | 2025-09-12 | 2025-09-22 | Completed
M5623 | P1113 | Structural Work | 2026-01-16 | 2026-01-26 | Delayed
M5624 | P1113 | Foundation | 2026-05-21 | 2026-05-21 | Completed
M5625 | P1114 | Land Acquisition | 2026-03-16 | 2026-03-21 | Completed
M5626 | P1114 | Major Construction | 2026-06-10 | 2026-06-20 | Completed
M5627 | P1114 | Structural Work | 2026-09-04 |  | Pending
M5628 | P1114 | Safety Inspection | 2026-11-29 |  | Pending
M5629 | P1114 | Final Handover | 2027-02-23 | 2027-03-30 | Delayed
M5630 | P1114 | Testing | 2027-05-20 | 2027-06-09 | Completed
M5631 | P1114 | Design Approval | 2027-08-14 | 2027-09-03 | Completed
M5632 | P1115 | Safety Inspection | 2022-10-22 |  | Pending
M5633 | P1115 | Foundation | 2023-01-31 | 2023-03-07 | Completed
M5634 | P1115 | Structural Work | 2023-05-13 | 2023-06-12 | Delayed
M5635 | P1115 | Land Acquisition | 2023-08-22 | 2023-09-26 | Delayed
M5636 | P1115 | Design Approval | 2023-12-01 | 2023-12-26 | Delayed
M5637 | P1115 | Testing | 2024-03-12 | 2024-03-22 | Completed
M5638 | P1115 | Major Construction | 2024-06-21 | 2024-07-01 | Completed
M5639 | P1116 | Testing | 2026-02-05 |  | Pending
M5640 | P1116 | Major Construction | 2026-07-08 |  | Pending
M5641 | P1116 | Final Handover | 2026-12-08 | 2026-12-13 | Delayed
M5642 | P1116 | N/A | 2027-05-10 | 2027-05-12 | Completed
M5643 | P1116 | Safety Inspection | 2027-10-10 |  | Pending
M5644 | P1117 | Major Construction | 2024-10-16 |  | Not Started
M5645 | P1117 | Land Acquisition | 2025-03-17 |  | Not Started
M5646 | P1117 | Structural Work | 2025-08-16 |  | Pending
M5647 | P1117 | Testing | 2026-01-15 | 2026-02-19 | Delayed
M5648 | P1118 | Safety Inspection | 2022-10-29 | 2022-12-09 | Delayed
M5649 | P1118 | Structural Work | 2023-02-01 | 2023-02-03 | Completed
M5650 | P1118 | Land Acquisition | 2023-05-07 | 2023-05-26 | Delayed
M5651 | P1118 | Major Construction | 2023-08-10 | 2023-08-10 | Completed
M5652 | P1118 | Testing | 2023-11-13 |  | Completed
M5653 | P1118 | Final Handover | 2024-02-16 | 2024-02-18 | Completed
M5654 | P1118 | N/A | 2024-05-21 | 2024-06-27 | Delayed
M5655 | P1119 | Testing | 2025-08-23 |  | In Progress
M5656 | P1119 | Land Acquisition | 2025-10-13 |  | Pending
M5657 | P1119 | Safety Inspection | 2025-12-03 | 2025-12-05 | Completed
M5658 | P1119 | Foundation | 2026-01-23 | 2026-03-14 | Delayed
M5659 | P1119 | Major Construction | 2026-03-15 | 2026-03-25 | Completed
M5660 | P1119 | Design Approval | 2026-05-05 | 2026-05-27 | Delayed
M5661 | P1119 | Structural Work | 2026-06-25 | 2026-07-30 | Completed
M5662 | P1120 | Major Construction | 2023-07-13 |  | Not Started
M5663 | P1120 | Structural Work |  |  | Not Started
M5664 | P1120 | Final Handover | 2023-11-29 |  | In Progress
M5665 | P1120 | Foundation | 2024-02-07 | 2024-02-09 | Completed
M5666 | P1120 | Testing | 2024-04-16 |  | Pending
M5667 | P1120 | Safety Inspection | 2024-06-25 | 2024-06-25 | Delayed
M5668 | P1120 | Design Approval | 2024-09-02 |  | Pending
M5669 | P1121 | Safety Inspection | 2025-04-06 |  | Not Started
M5670 | P1121 | Structural Work | 2025-07-26 | 2025-08-30 | Completed
M5671 | P1121 | Land Acquisition | 2025-11-15 | N/A | In Progress
M5672 | P1121 | Foundation | 2026-03-06 |  | In Progress
M5673 | P1121 | Major Construction | 2026-06-25 | 2026-07-15 | Completed
M5674 | P1122 | Design Approval | 2022-12-28 | 2023-01-17 | Completed
M5675 | P1122 | Testing | 2023-04-13 | 2023-04-15 | Completed
M5676 | P1122 | Foundation | 2023-07-28 | 2023-09-01 | Delayed
M5677 | P1122 | Safety Inspection | 2023-11-11 | 2024-01-10 | Completed
M5678 | P1123 | Final Handover | 2022-06-14 | 2022-08-13 | Delayed
M5679 | P1123 | Design Approval | 2022-10-03 | 2022-10-03 | Completed
M5680 | P1123 | Testing | 2023-01-22 | 2023-02-26 | Completed
M5681 | P1123 | Structural Work | 2023-05-12 | 2023-05-12 | Completed
M5682 | P1123 | Foundation | 2023-08-31 | 2023-09-05 | Completed
M5683 | P1124 | Foundation | 2022-07-04 |  | Not Started
M5684 | P1124 | Final Handover | 2022-10-19 | 2022-10-21 | Delayed
M5685 | P1124 | Land Acquisition | 2023-02-02 | 2023-02-02 | Completed
M5686 | P1124 | Safety Inspection | 2023-05-20 |  | In Progress
M5687 | P1125 | Major Construction | 2023-04-12 |  | In Progress
M5688 | P1125 | Structural Work | 2023-09-19 | 2023-09-24 | Completed
M5689 | P1125 | Land Acquisition | 2024-02-26 | 2024-02-28 | Completed
M5690 | P1125 | Safety Inspection | 2024-08-04 | 2024-08-04 | Completed
M5691 | P1126 | Final Handover | 2025-04-08 |  | Pending
M5692 | P1126 | Major Construction | 2025-09-25 | 2025-10-05 | Completed
M5693 | P1126 | Land Acquisition | 2026-03-14 |  | Pending
M5694 | P1126 | Structural Work | 2026-08-31 |  | Pending
M5695 | P1127 | Structural Work | 2025-11-23 |  | Not Started
M5696 | P1127 | Testing | 2026-01-17 | 2026-01-22 | Completed
M5697 | P1127 | Land Acquisition | 2026-03-12 |  | Not Started
M5698 | P1127 | Final Handover | 2026-05-06 |  | In Progress
M5699 | P1127 | Major Construction | 2026-06-29 | 2026-06-29 | Completed
M5700 | P1128 | Land Acquisition | 2024-05-30 | 2024-06-04 | Completed
M5701 | P1128 | Major Construction | 2024-08-27 | 2024-10-01 | Completed
M5702 | P1128 | Foundation | 2024-11-24 | 2024-11-26 | Completed
M5703 | P1128 | Design Approval | 2025-02-21 | 2025-03-13 | Completed
M5704 | P1128 | Testing | 2025-05-21 | 2025-05-26 | Completed
M5705 | P1128 | Final Handover | 2025-08-18 | 2025-09-22 | Completed
M5706 | P1129 | Foundation | 2024-05-04 | 2024-05-04 | Completed
M5707 | P1129 | Land Acquisition | 2024-09-14 | 2024-10-19 | Completed
M5708 | P1129 | Final Handover | 2025-01-25 | 2025-01-25 | Completed
M5709 | P1129 | Major Construction | 2025-06-07 | 2025-06-09 | Delayed
M5710 | P1129 | Testing | 2025-10-18 | 2025-10-23 | Completed
M5711 | P1130 | Design Approval | 2024-09-10 | 2024-11-09 | Delayed
M5712 | P1130 | Safety Inspection | 2024-10-26 | 2024-10-31 | Delayed
M5713 | P1130 | Structural Work | 2024-12-11 | 2024-12-13 | Completed
M5714 | P1130 | Major Construction | 2025-01-26 | 2025-02-15 | Completed
M5715 | P1130 | Final Handover | 2025-03-13 | 2025-03-23 | Completed
M5716 | P1131 | Testing | 2025-10-18 | 2025-10-28 | Delayed
M5717 | P1131 | Structural Work | 2025-12-19 | 2025-12-24 | Completed
M5718 | P1131 | Safety Inspection | 2026-02-19 | 2026-02-21 | Completed
M5719 | P1131 | Land Acquisition | 2026-04-22 | 2026-05-27 | Completed
M5720 | P1131 | Major Construction | 2026-06-23 | 2026-07-28 | Completed
M5721 | P1131 | Design Approval | 2026-08-24 | 2026-09-13 | Delayed
M5722 | P1132 | Safety Inspection | 2023-04-21 | 2023-04-23 | Delayed
M5723 | P1132 | Design Approval | 2023-07-24 | 2023-10-02 | Delayed
M5724 | P1132 | Major Construction | 2023-10-25 | 2023-12-22 | Delayed
M5725 | P1132 | Final Handover | 2024-01-27 | 2024-01-29 | Completed
M5726 | P1132 | Testing | 2024-04-29 | 2024-05-23 | Delayed
M5727 | P1132 | Structural Work | 2024-08-01 | 2024-10-17 | Delayed
M5728 | P1132 | Foundation | 2024-11-02 | 2024-11-22 | Delayed
M5729 | P1133 | Design Approval | 2023-12-08 | 2023-12-08 | Delayed
M5730 | P1133 | Safety Inspection | 2024-01-26 | 2024-03-01 | Completed
M5731 | P1133 | Structural Work | 2024-03-15 | null | Completed
M5732 | P1133 | Final Handover | 2024-05-04 | 2024-07-03 | Completed
M5733 | P1133 | Foundation | 2024-06-22 | 2024-07-27 | Completed
M5734 | P1133 | Major Construction | 2024-08-10 | 2024-08-15 | Delayed
M5735 | P1134 | Structural Work | 2025-09-06 | 2025-09-16 | Completed
M5736 | P1134 | Design Approval | 2025-12-01 | 2025-12-21 | Completed
M5737 | N/A | Testing | 2026-02-24 | 2026-03-16 | Delayed
M5738 | P1134 | Foundation | 2026-05-21 | 2026-07-20 | Completed
M5739 | P1134 | Major Construction | 2026-08-15 | 2026-09-04 | Completed
M5740 | P1134 | Final Handover | 2026-11-08 | 2026-11-28 | Completed
M5741 | P1134 | Safety Inspection | 2027-02-02 | 2027-02-07 | Completed
M5742 | P1135 | Safety Inspection | 2026-02-11 | 2026-02-21 | Delayed
M5743 | P1135 | Testing | 2026-06-06 | 2026-06-08 | Completed
M5744 | P1135 | Major Construction | 2026-09-29 | 2026-10-01 | Delayed
M5745 | N/A | Structural Work | 2027-01-21 | 2027-01-26 | Delayed
M5746 | P1135 | Foundation | 2027-05-16 | 2027-07-15 | Completed
M5747 | P1136 | Land Acquisition | 2024-05-12 |  | In Progress
M5748 | P1136 | Final Handover |  |  | Pending
M5749 | P1136 | Testing | 2024-12-05 | 2025-01-09 | Delayed
M5750 | P1136 | Safety Inspection | 2025-03-18 |  | Not Started
M5751 | P1136 | Design Approval | 2025-06-29 |  | In Progress
M5752 | P1137 | Final Handover | null | 2025-02-26 | Completed
M5753 | P1137 | Major Construction | 2025-07-02 | 2025-07-02 | Delayed
M5754 | N/A | Structural Work | 2025-11-08 |  | Pending
M5755 | P1137 | Safety Inspection | 2026-03-16 |  | In Progress
M5756 | P1137 | Testing | 2026-07-22 | 2026-08-11 | Completed
M5757 | P1138 | Land Acquisition | 2022-10-19 | 2022-10-29 | Completed
M5758 | P1138 | Major Construction | 2023-03-08 | 2023-04-12 | Completed
M5759 | P1138 | Structural Work | 2023-07-27 | 2023-07-27 | Completed
M5760 | P1138 | Foundation | 2023-12-14 | 2024-01-18 | Completed
M5761 | P1139 | Land Acquisition | 2023-11-04 | 2023-11-14 | Completed
M5762 | P1139 | Foundation | 2024-01-21 | 2024-03-21 | Completed
M5763 | P1139 | Major Construction | 2024-04-08 | 2024-04-08 | Completed
M5764 | P1139 | Final Handover | 2024-06-25 |  | Not Started
M5765 | P1139 | Structural Work | 2024-09-11 | 2024-10-16 | Delayed
M5766 | P1139 | Design Approval | 2024-11-28 |  | Not Started
M5767 | P1140 | Major Construction | 2022-06-24 | 2022-07-04 | Completed
M5768 | P1140 | Safety Inspection | 2022-10-24 | 2022-10-24 | Completed
M5769 | P1140 | Testing | 2023-02-23 | 2023-03-15 | Completed
M5770 | P1140 | Final Handover | 2023-06-25 | 2023-06-30 | Completed
M5771 | P1141 | Foundation | 2024-09-30 | 2024-10-05 | Completed
M5772 | P1141 | Major Construction | 2025-03-15 | 2025-04-19 | Completed
M5773 | P1141 | Testing | 2025-08-27 | 2025-10-26 | Completed
M5774 | P1141 | Design Approval | 2026-02-09 | 2026-02-09 | Completed
M5775 | P1142 | Final Handover | 2024-12-14 | 2025-01-19 | Delayed
M5776 | P1142 | Safety Inspection | 2025-02-01 | 2025-03-08 | Completed
M5777 | P1142 | Structural Work | 2025-03-23 | 2025-03-28 | Completed
M5778 |  | Testing | 2025-05-11 | 2025-05-21 | Delayed
M5779 | P1142 | N/A | 2025-06-29 | 2025-07-09 | Completed
M5780 | P1143 | Safety Inspection | 2023-05-29 |  | In Progress
M5781 | P1143 | Structural Work | 2023-09-17 | 2023-09-22 | Completed
M5782 | P1143 | Foundation | 2024-01-06 | 2024-01-26 | Completed
M5783 | P1143 | Design Approval | 2024-04-27 |  | In Progress
M5784 | P1143 | Final Handover | 2024-08-16 |  | Not Started
M5785 | P1143 | Land Acquisition | 2024-12-05 |  | In Progress
M5786 | P1143 | Major Construction | 2025-03-26 | 2025-05-25 | Completed
M5787 | P1144 | Safety Inspection | 2025-11-01 | 2025-12-06 | Completed
M5788 | P1144 | Structural Work | 2026-03-04 | 2026-03-04 | Completed
M5789 | P1144 | Testing | 2026-07-05 | 2026-07-05 | Delayed
M5790 | P1144 | Design Approval | 2026-11-04 | 2026-11-04 | Delayed
M5791 | P1144 | Major Construction | 2027-03-07 | 2027-04-11 | Completed
M5792 | P1144 | Foundation | 2027-07-08 | 2027-07-08 | Completed
M5793 | P1145 | Land Acquisition | 2025-12-14 | 2026-01-18 | Completed
M5794 | P1145 | Major Construction | 2026-06-11 | 2026-06-11 | Completed
M5795 | P1145 | Testing | 2026-12-07 | 2026-12-09 | Delayed
M5796 | P1145 | Design Approval | 2027-06-04 | 2027-07-09 | Completed
M5797 | P1146 | Foundation | 2022-07-22 |  | Pending
M5798 | P1146 | Final Handover | 2022-10-10 |  | In Progress
M5799 | P1146 | Safety Inspection | 2022-12-29 |  | N/A
M5800 | P1146 | Structural Work | 2023-03-19 |  | In Progress
M5801 | P1147 | Foundation | 2024-05-17 | 2024-05-17 | Completed
M5802 | P1147 | Safety Inspection | 2024-09-04 |  | In Progress
M5803 | P1147 | Land Acquisition | 2024-12-22 | 2024-12-22 | Delayed
M5804 | P1147 | Final Handover | 2025-04-11 |  | Pending
M5805 | P1147 | Testing | 2025-07-29 |  | Pending
M5806 | P1147 | Design Approval | 2025-11-16 |  | Pending
M5807 | P1148 | Safety Inspection | N/A | 2024-04-16 | Delayed
M5808 | P1148 | Design Approval | 2024-08-05 | 2024-08-05 | Completed
M5809 | P1148 | Major Construction | 2024-12-21 | 2025-01-07 | Delayed
M5810 | P1148 | Land Acquisition | 2025-05-09 |  | Pending
M5811 | P1148 | Structural Work | 2025-09-24 | 2025-10-09 | Delayed
M5812 | P1149 | Safety Inspection | 2023-08-09 |  | Not Started
M5813 | P1149 | Foundation | 2023-11-09 | 2023-12-14 | Delayed
M5814 | P1149 | Design Approval | 2024-02-09 | 2024-02-19 | Completed
M5815 | P1149 | Final Handover | 2024-05-11 | 2024-05-11 | Delayed
M5816 | P1150 | Design Approval | 2022-12-04 | 2023-01-08 | Completed
M5817 | P1150 | Major Construction | 2023-02-06 | 2023-04-07 | Completed
M5818 | P1150 | Safety Inspection | 2023-04-11 | 2023-04-21 | Completed
M5819 | P1150 | Foundation | 2023-06-14 | 2023-07-21 | Delayed
M5820 | P1150 | Testing | 2023-08-16 | 2023-10-19 | Delayed
M5821 | P1150 | Structural Work | 2023-10-19 | 2023-12-11 | Delayed
M5822 | P1150 | Final Handover | 2023-12-22 | 2024-01-19 | Delayed
M5823 | P1151 | Final Handover | 2024-11-02 | 2024-11-02 | Completed
M5824 | P1151 | Land Acquisition | 2025-02-25 | 2025-02-25 | Completed
M5825 | P1151 | Testing |  | 2025-08-19 | Delayed
M5826 | P1151 | Structural Work | 2025-10-12 | 2025-10-12 | Completed
M5827 | P1151 | Design Approval | 2026-02-04 | 2026-02-09 | Completed
M5828 | P1151 | Safety Inspection | 2026-05-30 | 2026-06-01 | Delayed
M5829 | P1152 | Structural Work | 2025-09-21 |  | In Progress
M5830 | P1152 | Land Acquisition | 2026-01-26 |  | Not Started
M5831 | P1152 | Safety Inspection | 2026-06-02 | 2026-07-07 | Completed
M5832 | P1152 | Design Approval | 2026-10-07 | 2026-11-11 | Completed
M5833 | P1152 | Final Handover | 2027-02-11 |  | Pending
M5834 | P1153 | Foundation | 2023-12-04 |  | Not Started
M5835 | P1153 | Safety Inspection | 2024-01-24 | 2024-03-24 | Completed
M5836 | P1153 | Major Construction | 2024-03-15 | 2024-05-14 | Delayed
M5837 | P1153 | Land Acquisition | 2024-05-05 | 2024-06-09 | Completed
M5838 | P1153 | Testing | 2024-06-24 | 2024-08-23 | Completed
M5839 | P1153 | Structural Work | 2024-08-14 |  | Not Started
M5840 | P1153 | Design Approval | 2024-10-04 | 2024-10-04 | Completed
M5841 | P1154 | Foundation | 2025-11-30 | 2025-12-02 | Completed
M5842 | P1154 | Safety Inspection | 2026-01-19 | 2026-03-20 | Delayed
M5843 | P1154 | Structural Work | 2026-03-10 |  | Pending
M5844 | P1154 | Design Approval | 2026-04-30 |  | Pending
M5845 | P1154 | Final Handover | 2026-06-19 | 2026-06-21 | Completed
M5846 | P1154 | Testing | 2026-08-08 |  | Not Started
M5847 | P1155 | Safety Inspection | 2025-07-23 | 2025-08-12 | Delayed
M5848 | P1155 | Testing | 2025-11-04 | 2025-11-06 | Completed
M5849 | P1155 | Structural Work | 2026-02-17 | 2026-03-24 | Delayed
M5850 | P1155 | Design Approval | 2026-06-01 | 2026-06-01 | Completed
M5851 | P1155 | Major Construction | 2026-09-14 | 2026-09-14 | Completed
M5852 | P1155 | Land Acquisition | 2026-12-27 | 2027-01-16 | Completed
M5853 | P1156 | Structural Work | 2024-07-02 | 2024-08-31 | Completed
M5854 | P1156 | Final Handover | 2024-08-27 |  | In Progress
M5855 | P1156 | Testing | 2024-10-23 | 2024-10-25 | Completed
M5856 | P1156 | Design Approval | 2024-12-18 | 2024-12-23 | Completed
M5857 | P1156 | Foundation | 2025-02-13 | 2025-02-18 | Completed
M5858 | P1156 | Land Acquisition | 2025-04-10 |  | In Progress
M5859 | P1157 | Design Approval | 2025-06-16 | 2025-08-15
M5860 | P1157 | Testing | 2025-10-08 | 2025-10-08 | Completed
M5861 | P1157 | Land Acquisition | 2026-01-31 |  | Not Started
M5862 | P1157 | Major Construction | 2026-05-25 | 2026-06-14 | Completed
M5863 | P1158 | Structural Work | 2023-03-31 | 2023-04-02 | Delayed
M5864 | P1158 | Testing | 2023-06-01 | 2023-06-11 | Completed
M5865 | P1158 | Safety Inspection | 2023-08-01 | 2023-08-21 | Delayed
M5866 | P1158 | Foundation | 2023-10-02 | 2023-10-12 | Completed
M5867 | P1158 | Design Approval | 2023-12-02 | 2023-12-22 | Delayed
M5868 | P1158 | Land Acquisition | 2024-02-02 | 2024-02-07 | Completed
M5869 | P1158 | Final Handover | 2024-04-03 | 2024-04-05 | Completed
M5870 | P1159 | Structural Work | 2024-04-10 | 2024-06-09 | Delayed
M5871 | P1159 | Foundation | 2024-08-04 | 2024-08-06 | Completed
M5872 | P1159 | Design Approval | 2024-11-28 | 2024-12-03 | Completed
M5873 | P1159 | Land Acquisition | 2025-03-24 |  | Not Started
M5874 | P1159 | Major Construction | 2025-07-18 |  | Pending
M5875 | P1159 | Testing | 2025-11-11 |  | Not Started
M5876 | P1160 | Design Approval | 2023-10-05 | 2023-12-04 | Delayed
M5877 | P1160 | Structural Work | 2023-11-27 | 2024-01-01 | Delayed
M5878 | P1160 | Major Construction | 2024-01-20 | 2024-01-22 | Completed
M5879 | P1160 | Safety Inspection | 2024-03-13 | 2024-04-02 | Completed
M5880 | P1160 | Final Handover | 2024-05-05 | 2024-05-25 | Completed
M5881 | P1161 | Safety Inspection | 2025-11-29 | 2025-12-19 | Completed
M5882 | P1161 | Land Acquisition | 2026-05-16 | 2026-05-26 | Delayed
M5883 | P1161 | Final Handover | 2026-10-31 | 2026-12-05 | Completed
M5884 | P1161 | Structural Work | 2027-04-17 | 2027-04-19 | Completed
M5885 | P1162 | Safety Inspection | 2022-11-27 | 2023-01-01 | Completed
M5886 | P1162 | Design Approval | 2023-01-15 | 2023-02-19 | Completed
M5887 | P1162 | Final Handover | 2023-03-05 | 2023-03-15 | Completed
M5888 | P1162 | Foundation | 2023-04-23 |  | In Progress
M5889 | P1163 | Safety Inspection | 2022-06-26 |  | Pending
M5890 | P1163 | Design Approval | 2022-08-20 | 2022-09-24 | Completed
M5891 | P1163 | Foundation | 2022-10-14 | 2022-10-19 | Delayed
M5892 | P1163 | Structural Work | 2022-12-08 | 2023-01-18 | Delayed
M5893 | P1163 | Land Acquisition | 2023-02-01 | 2023-02-26 | Delayed
M5894 | P1164 | Land Acquisition | 2024-12-11 | 2024-12-21 | Completed
M5895 | P1164 | Major Construction | 2025-02-10 | 2025-02-12 | Completed
M5896 | P1164 | Testing | 2025-04-13 |  | Pending
M5897 | P1164 | Foundation | 2025-06-13 | 2025-06-18 | Completed
M5898 | P1164 | Final Handover | 2025-08-14 | 2025-09-18 | Delayed
M5899 | P1164 | Structural Work | 2025-10-14 |  | Not Started
M5900 | P1165 | Structural Work | 2025-04-12 | 2025-04-12 | Completed
M5901 | P1165 | Foundation | 2025-08-14 | 2025-08-24 | Completed
M5902 | P1165 | Safety Inspection | 2025-12-16 | 2026-01-05 | Completed
M5903 | P1165 | Testing | 2026-04-19 | 2026-04-24 | Completed
M5904 | P1165 | Final Handover | 2026-08-21 | 2026-08-31 | Completed
M5905 | P1166 | Safety Inspection | 2022-05-26 | 2022-05-31 | Completed
M5906 | P1166 | Design Approval | 2022-09-20 | 2022-12-07 | Delayed
M5907 | P1166 | Foundation | N/A | 2023-01-17 | Completed
M5908 | P1166 | Land Acquisition | 2023-05-12 | 2023-06-16 | Completed
M5909 | P1167 | Testing | 2022-09-06 | 2022-11-05 | Completed
M5910 | P1167 | N/A | 2022-10-30 |  | Not Started
M5911 | P1167 | Safety Inspection | 2022-12-22 |  | In Progress
M5912 | P1167 | Land Acquisition | 2023-02-14 |  | Not Started
M5913 | P1167 | Foundation | 2023-04-09 |  | In Progress
M5914 | P1167 | Major Construction | 2023-06-01 | 2023-07-06 | Delayed
M5915 | P1167 | Final Handover | 2023-07-25 | 2023-08-14 | Completed
M5916 | P1168 | Foundation | 2025-04-23 | 2025-06-22 | Completed
M5917 | P1168 | Safety Inspection | 2025-05-29 | 2025-06-03 | Delayed
M5918 | P1168 | Final Handover | 2025-07-04 | 2025-07-24 | Completed
M5919 | P1168 | Design Approval | 2025-08-09 | 2025-08-14 | Completed
M5920 | P1168 | Structural Work | 2025-09-14 | 2025-11-13 | Completed
M5921 | P1168 | Major Construction | 2025-10-20 | 2025-10-20 | Completed
M5922 | P1169 | Foundation | 2025-10-17 |  | Pending
M5923 | P1169 | Structural Work | 2026-01-02 |  | In Progress
M5924 | P1169 | Final Handover | 2026-03-21 | 2026-03-31 | Completed
M5925 | P1169 | Testing | 2026-06-06 |  | Completed
M5926 | P1169 | Design Approval | 2026-08-23 | 2026-09-02 | Completed
M5927 | N/A | Land Acquisition | 2026-11-08 |  | In Progress
M5928 | P1170 | Land Acquisition | 2023-06-14 | 2023-08-05 | Delayed
M5929 | P1170 | Testing | 2023-09-04 | 2023-09-09 | Completed
M5930 | P1170 | Major Construction | N/A | 2024-02-04 | Delayed
M5931 | P1170 | Safety Inspection | 2024-02-15 | 2024-02-15 | Delayed
M5932 | P1170 | Foundation | 2024-05-07 |  | Pending
M5933 | P1171 | Major Construction | 2023-01-23 | 2023-02-02 | Completed
M5934 | P1171 | Land Acquisition | 2023-04-15 | 2023-04-15 | Completed
M5935 | P1171 | Structural Work | 2023-07-05 | 2023-07-07 | Completed
M5936 | P1171 | Final Handover | 2023-09-25 | 2023-09-25 | Delayed
M5937 | P1172 | Safety Inspection | 2025-03-30 |  | Not Started
M5938 | P1172 | Design Approval | 2025-08-10 |  | Not Started
M5939 | P1172 | Structural Work | 2025-12-21 | 2025-12-23 | Delayed
M5940 | P1172 | Foundation | 2026-05-03 | 2026-05-08 | Completed
M5941 | P1173 | Testing | 2022-07-08 | 2022-07-18 | Delayed
M5942 | P1173 | Foundation | 2022-10-12 | 2022-10-17 | Completed
M5943 | P1173 | Safety Inspection | 2023-01-16 | 2023-01-26 | Delayed
M5944 | P1173 | Structural Work | 2023-04-22 | 2023-05-12 | Completed
M5945 | P1173 | Land Acquisition | 2023-07-27 | 2023-08-01 | Delayed
M5946 | P1173 | Major Construction | 2023-10-31 | 2023-11-20 | Completed
M5947 | P1174 | Safety Inspection | 2023-04-02 |  | In Progress
M5948 | P1174 | Land Acquisition | 2023-09-28 | 2023-10-18 | Delayed
M5949 | P1174 | Final Handover | 2024-03-25 |  | Pending
M5950 | P1174 | Structural Work | 2024-09-20 | 2024-11-19 | Delayed
M5951 | P1175 | Final Handover | 2022-10-30 |  | In Progress
M5952 | P1175 | Land Acquisition | 2022-12-29 | 2023-02-27 | Completed
M5953 | P1175 | Foundation | 2023-02-27 | 2023-03-04 | Delayed
M5954 | P1175 | Major Construction | 2023-04-29 | 2023-06-03 | Completed
M5955 | P1175 | Testing | 2023-06-28 | 2023-07-08 | Completed
M5956 | P1175 | Design Approval | 2023-08-27 | 2023-10-26 | Completed
M5957 | P1176 | Design Approval | 2025-04-14 |  | Not Started
M5958 | P1176 | Major Construction | 2025-07-07 |  | Not Started
M5959 | P1176 | Testing | 2025-09-29 |  | In Progress
M5960 | P1176 | Foundation | 2025-12-23 | N/A | Completed
M5961 | P1176 | Structural Work | 2026-03-17 |  | Pending
M5962 | P1176 | Safety Inspection | 2026-06-09 |  | Pending
M5963 | P1176 | Final Handover | 2026-09-01 | 2026-10-06 | Completed
M5964 | P1177 | Foundation | 2025-07-19 | 2025-07-24 | Completed
M5965 | P1177 | Land Acquisition | 2025-08-25 | 2025-09-14 | Completed
M5966 |  | Final Handover | 2025-09-30 | 2025-11-29 | Completed
M5967 | P1177 | Testing | 2025-11-06 | 2025-11-26 | Completed
M5968 | P1177 | Structural Work | 2025-12-12 | 2026-02-10 | Completed
M5969 | P1177 | Major Construction | 2026-01-18 | 2026-02-22 | Completed
M5970 | P1178 | Testing | 2023-08-16 | 2023-09-05 | Completed
M5971 | P1178 | Land Acquisition | 2023-12-07 | 2023-12-17 | Delayed
M5972 | P1178 | Major Construction | 2024-03-29 | 2024-03-31 | Completed
M5973 | P1178 | Final Handover | 2024-07-20 | 2024-08-09 | Completed
M5974 | P1178 | Foundation | 2024-11-10 | 2025-01-09 | Completed
M5975 | p1178 | Safety Inspection | 2025-03-03 | 2025-03-03 | Completed
M5976 | P1179 | Land Acquisition | 2023-03-22 | 2023-04-01 | Completed
M5977 | P1179 | Structural Work | 2023-08-22 | 2023-08-27 | Completed
M5978 | P1179 | Foundation | 2024-01-22 |  | Pending
M5979 | P1179 | Testing | 2024-06-22 | 2024-08-21 | Completed
M5980 | P1179 | Major Construction | 2024-11-22 |  | In Progress
M5981 | P1180 | Structural Work | 2022-07-14 | 2022-09-12 | Delayed
M5982 | P1180 | Design Approval | 2022-10-21 |  | Pending
M5983 | P1180 | Land Acquisition | 2023-01-28 | 2023-01-28 | Completed
M5984 | P1180 | Final Handover | 2023-05-06 | 2023-05-11 | Completed
M5985 | P1180 | Testing | 2023-08-13 | 2023-09-17 | Completed
M5986 | P1181 | Design Approval | 2023-11-24 |  | Pending
M5987 | P1181 | Major Construction | 2024-02-09 | 2024-02-27 | Delayed
M5988 | P1181 | Final Handover | 2024-04-27 | 2024-06-26 | Completed
M5989 | P1181 | N/A | 2024-07-13 |  | In Progress
M5990 | P1182 | Foundation | 2024-10-06 | 2024-10-06 | Completed
M5991 | P1182 | Safety Inspection | 2025-01-02 | 2025-02-06 | Completed
M5992 | P1182 | Major Construction | 2025-04-01 | 2025-04-03 | Completed
M5993 | P1182 | Testing | 2025-06-28 | 2025-06-28 | Completed
M5994 | P1182 | Design Approval | 2025-09-25 | 2025-11-24 | Delayed
M5995 | P1182 | Final Handover | 2025-12-22 | 2026-01-11 | Completed
M5996 | P1183 | Design Approval | 2024-01-20 | 2024-03-20 | Completed
M5997 | P1183 | Final Handover | 2024-03-29 | 2024-03-29 | Completed
M5998 | P1183 | Foundation | 2024-06-06 | 2024-06-11 | Completed
M5999 | P1183 | Structural Work | 2024-08-14 |  | Pending
M6000 | P1183 | Major Construction | 2024-10-21 | 2024-10-31
M6001 | P1183 | Land Acquisition | 2024-12-29 | 2025-01-08 | Completed
M6002 | P1183 | Testing | 2025-03-08 |  | In Progress
M6003 | P1184 | Safety Inspection | 2025-05-09 |  | In Progress
M6004 | P1184 | Foundation | 2025-08-12 |  | In Progress
M6005 | P1184 | Structural Work | 2025-11-15 | 2025-12-20 | Delayed
M6006 | P1184 | Design Approval | 2026-02-18 | 2026-04-24 | Delayed
M6007 | P1184 | Land Acquisition | 2026-05-24 | 2026-06-28 | Completed
M6008 | P1185 | Foundation | 2024-01-15 |  | Not Started
M6009 | P1185 | Structural Work | 2024-04-14 |  | Pending
M6010 | P1185 | Safety Inspection | 2024-07-12 | 2024-07-14 | Completed
M6011 | P1185 | Major Construction | 2024-10-10 | 2024-12-09 | Delayed
M6012 | P1186 | Structural Work | 2023-06-01 | 2023-07-06 | Completed
M6013 | P1186 | Safety Inspection | 2023-09-24 | 2023-11-23 | Delayed
M6014 | P1186 | Final Handover | 2024-01-18 | 2024-02-22 | N/A
M6015 | P1186 | Testing | 2024-05-12 | 2024-06-01 | Completed
M6016 | P1187 | Final Handover | 2024-02-29 | 2024-04-04 | Completed
M6017 | P1187 | Land Acquisition | 2024-05-08 | 2024-06-12 | Completed
M6018 | P1187 | Safety Inspection | 2024-07-16 | 2024-07-26 | Completed
M6019 | P1187 | Foundation | 2024-09-23 | 2024-10-03 | Completed
M6020 | P1187 | Structural Work | 2024-12-01 | 2024-12-21 | Completed
M6021 | P1188 | Final Handover | 2022-05-26 | 2022-06-05 | Delayed
M6022 | P1188 | N/A | 2022-10-05 | 2022-10-25 | Completed
M6023 | P1188 | Structural Work | 2023-02-15 | 2023-03-07 | Completed
M6024 | P1188 | Design Approval | 2023-06-27 | 2023-06-27 | Delayed
M6025 | P1189 | Safety Inspection | 2022-03-23 | 2022-03-23 | Completed
M6026 | P1189 | Structural Work | 2022-05-11 | 2022-06-15 | Completed
M6027 | P1189 | Foundation | 2022-06-29 |  | Pending
M6028 | P1189 | Final Handover | 2022-08-17 | 2022-08-19 | Completed
M6029 | P1190 | Final Handover | 2022-10-22 | 2022-12-21 | Completed
M6030 | P1190 | Safety Inspection | 2023-01-27 | 2023-02-06 | Completed
M6031 | P1190 | Land Acquisition | 2023-05-04 | 2023-05-14 | Completed
M6032 | P1190 | Major Construction | 2023-08-09 | 2023-08-14 | Completed
M6033 | P1190 | Structural Work | 2023-11-14 | 2023-12-04 | Completed
M6034 | P1190 |  | 2024-02-19 | 2024-02-24 | Completed
M6035 | P1190 | Design Approval | 2024-05-26 | 2024-06-15 | Completed
M6036 | P1191 | Safety Inspection | 2023-07-20 | 2023-08-24 | Completed
M6037 | P1191 | Land Acquisition | 2023-09-25 | 2023-10-30 | Completed
M6038 | P1191 | Structural Work | 2023-12-01 | 2024-01-05 | Completed
M6039 | P1191 | Foundation | 2024-02-07 | 2024-02-07 | Completed
M6040 | P1191 | Major Construction | 2024-04-14 | 2024-05-04 | Completed
M6041 | p1191 | Design Approval | 2024-06-20 | 2024-07-25 | Delayed
M6042 | P1192 | Major Construction | 2022-03-12 | 2022-03-17 | Completed
M6043 | P1192 | Land Acquisition | 2022-05-03 | 2022-05-03 | Completed
M6044 | P1192 | Testing | 2022-06-24 | 2022-07-14 | Completed
M6045 | P1192 | Structural Work | 2022-08-15 | 2022-08-20 | Completed
M6046 | P1192 | Safety Inspection | 2022-10-06 | 2022-10-08 | Delayed
M6047 | P1192 | Design Approval | 2022-11-27 | 2023-01-26 | Completed
M6048 | P1192 | Foundation | 2023-01-18 | 2023-02-07 | Completed
M6049 | P1193 | Major Construction | 2026-03-15 |  | Pending
M6050 | P1193 | Land Acquisition | 2026-07-10 |  | Not Started
M6051 | P1193 | Foundation | 2026-11-04 | 2026-11-09 | Completed
M6052 | P1193 | Final Handover | 2027-03-01 | 2027-04-30 | Delayed
M6053 | P1193 | Structural Work | 2027-06-26 | 2027-07-01 | Completed
M6054 | P1193 | Safety Inspection | 2027-10-21 |  | In Progress
M6055 | P1194 | Safety Inspection | 2025-06-11 | 2025-07-01 | Delayed
M6056 | P1194 | Testing | 2025-08-05 | 2025-09-12 | Delayed
M6057 | P1194 | Major Construction | 2025-09-29 |  | Not Started
M6058 | P1194 | Foundation | 2025-11-24 | 2026-01-01 | Delayed
M6059 | P1194 | Design Approval | 2026-01-18 | 2026-03-01 | Delayed
M6060 | P1194 | Structural Work | 2026-03-14 | 2026-05-27 | Delayed
M6061 | P1195 |  | 2023-02-26 | 2023-02-28 | Completed
M6062 | P1195 | Major Construction | 2023-07-11 | 2023-09-02 | Delayed
M6063 | P1195 | Testing | 2023-11-23 |  | In Progress
M6064 | P1195 | Land Acquisition | 2024-04-06 | 2024-06-05 | Completed
M6065 | P1195 | Design Approval | 2024-08-19 | 2024-10-25 | Delayed
M6066 | P1195 | Structural Work | 2025-01-01 | 2025-01-06 | Completed
M6067 | P1196 | Structural Work | 2025-10-04 | 2025-12-03 | Completed
M6068 | P1196 | Final Handover | 2025-12-17 | 2026-01-06 | Delayed
M6069 | P1196 | Design Approval | 2026-03-01 | 2026-03-01 | Completed
M6070 | P1196 | Land Acquisition | 2026-05-14 | 2026-05-16 | Completed
M6071 | P1196 | Testing | 2026-07-27 | 2026-09-25 | Completed
M6072 | P1196 | Major Construction | 2026-10-09 | 2026-11-15 | Delayed
M6073 | P1197 | Final Handover | 2023-12-04 |  | Pending
M6074 | P1197 | Safety Inspection | 2024-03-11 | 2024-03-16 | Completed
M6075 | P1197 | Land Acquisition | 2024-06-18 |  | In Progress
M6076 | P1197 | Testing | 2024-09-24 |  | Not Started
M6077 | P1198 |  | 2024-02-10 | 2024-03-01 | Completed
M6078 | P1198 | Final Handover | 2024-06-28 | 2024-08-27 | Completed
M6079 | P1198 | Testing | 2024-11-14 | 2024-11-14 | Completed
M6080 | P1198 | Design Approval | 2025-04-02 |  | In Progress
M6081 | P1199 | Safety Inspection | 2025-03-28 | 2025-03-30 | Completed
M6082 | P1199 | Final Handover | 2025-05-15 |  | In Progress
M6083 | P1199 | Testing | 2025-07-02 | 2025-08-31 | Completed
M6084 | P1199 | Design Approval | 2025-08-19 | 2025-08-24 | Completed
M6085 | P1199 | Structural Work | 2025-10-06 | 2025-10-16 | Delayed
M6086 | P1199 | Land Acquisition | 2025-11-23 |  | In Progress
M6087 | P1200 | Testing | 2023-05-19 | 2023-06-08 | Completed
M6088 | P1200 | Structural Work | 2023-10-23 |  | Not Started
M6089 | P1200 | Final Handover | 2024-03-28 |  | Pending
M6090 | P1200 | Foundation | 2024-09-01 |  | Not Started
M6091 | P1200 | Major Construction | 2025-02-05 | 2025-02-25 | Delayed
M6092 | P1201 | Testing | 2023-08-09 | 2023-08-19 | Completed
M6093 | P1201 | Safety Inspection | 2023-10-18 | 2023-12-17 | Completed
M6094 | P1201 | Final Handover | 2023-12-27 | 2024-02-25 | Completed
M6095 | P1201 | Land Acquisition | 2024-03-07 |  | Not Started
M6096 | P1201 | Design Approval | 2024-05-16 | 2024-07-15 | Delayed
M6097 | P1201 | Structural Work | 2024-07-25 | 2024-09-13 | Delayed
M6098 | P1202 | Final Handover | 2024-04-01 |  | In Progress
M6099 | P1202 | Structural Work | 2024-08-15 | 2024-09-11 | Delayed
M6100 | P1202 | Testing | 2024-12-29 |  | Not Started
M6101 | P1202 | Safety Inspection | 2025-05-14 | 2025-05-14 | Completed
M6102 | P1203 | Testing | 2026-03-15 |  | Not Started
M6103 | P1203 | Structural Work | 2026-07-04 | 2026-07-14 | Completed
M6104 | P1203 | Final Handover | 2026-10-23 |  | In Progress
M6105 | P1203 | Land Acquisition | 2027-02-11 |  | Pending
M6106 | P1203 | Major Construction | 2027-06-02 | 2027-06-22 | Completed
M6107 | P1203 | Foundation | 2027-09-21 |  | Not Started
M6108 | P1203 | Safety Inspection | 2028-01-10 | 2028-01-15 | Delayed
M6109 | P1204 | Foundation | 2022-05-25 | 2022-05-30 | N/A
M6110 | P1204 | Final Handover | 2022-08-22 | 2022-09-01 | Completed
M6111 | P1204 | Design Approval | 2022-11-19 | 2022-11-19 | Completed
M6112 | P1204 | Major Construction | 2023-02-16 |  | In Progress
M6113 | P1204 | Safety Inspection | 2023-05-16 | 2023-06-20 | Completed
M6114 | P1204 | Testing | 2023-08-13 | 2023-09-02 | Delayed
M6115 | P1204 | Land Acquisition | 2023-11-10 |  | Pending
M6116 | P1205 | Testing | 2023-12-19 | 2024-01-08 | Delayed
M6117 | P1205 | Design Approval | 2024-03-25 | N/A | Delayed
M6118 |  | Major Construction | 2024-07-01 | 2024-08-05 | Completed
M6119 | P1205 | Land Acquisition | 2024-10-06 | 2024-12-05 | Completed
M6120 | P1206 | Final Handover | 2026-02-20 | 2026-04-21 | Completed
M6121 | P1206 | Structural Work | 2026-05-26 |  | Pending
M6122 | P1206 | Design Approval | 2026-08-30 | 2026-09-09 | Completed
M6123 | P1206 | Safety Inspection | 2026-12-03 | 2026-12-08 | Completed
M6124 | P1206 | Testing | 2027-03-09 |  | Pending
M6125 | P1206 | Foundation | 2027-06-12 | 2027-07-17 | Delayed
M6126 | P1207 | Land Acquisition | 2025-08-04 |  | In Progress
M6127 | P1207 | Structural Work | 2025-09-30 |  | Not Started
M6128 | P1207 | Design Approval | 2025-11-26 | 2025-12-06 | Completed
M6129 | P1207 | Foundation | 2026-01-22 | 2026-02-11 | Completed
M6130 | P1208 | Testing | 2024-08-01 |  | Not Started
M6131 | P1208 | Design Approval | N/A |  | Not Started
M6132 | P1208 | Structural Work | 2025-05-14 | 2025-06-03 | Delayed
M6133 | P1208 | Foundation | 2025-10-04 | 2025-10-24 | Delayed
M6134 | P1209 | Safety Inspection | 2023-01-11 | 2023-01-13 | Delayed
M6135 | P1209 | Testing | 2023-04-06 | 2023-04-16 | Completed
M6136 | P1209 | Foundation | 2023-06-30 | 2023-08-04 | Delayed
M6137 | P1209 | Design Approval | 2023-09-23 | 2023-09-23 | Completed
M6138 | P1209 | Land Acquisition | 2023-12-17 | 2023-12-19
M6139 | P1209 | Final Handover | 2024-03-11 | 2024-05-10 | Completed
M6140 | P1210 | Safety Inspection | 2023-10-17 | 2023-10-19 | Completed
M6141 | P1210 | Foundation | 2023-11-27 | 2024-02-12 | Delayed
M6142 | P1210 | Final Handover | 2024-01-07 | 2024-02-10 | Delayed
M6143 | P1210 | Major Construction | 2024-02-16 | 2024-04-27 | Delayed
M6144 | P1210 | Testing | 2024-03-28 | 2024-03-30 | Completed
M6145 | P1210 | Structural Work | 2024-05-08 | 2024-05-08 | Delayed
M6146 | P1211 | Foundation | 2025-04-02 | 2025-04-07 | Delayed
M6147 | P1211 | Testing | 2025-05-30 | 2025-05-30 | Completed
M6148 | P1211 | Structural Work | 2025-07-26 | 2025-07-26 | Completed
M6149 | p1211 | Safety Inspection | 2025-09-22 | 2025-09-24 | Completed
M6150 | P1211 | Land Acquisition |  | 2026-01-17 | Completed
M6151 | P1211 | Design Approval | 2026-01-15 | 2026-02-19 | Completed
M6152 | P1212 | Foundation | 2025-09-07 |  | Not Started
M6153 | P1212 | Structural Work | 2025-12-04 | 2025-12-09 | Completed
M6154 | P1212 | Land Acquisition | 2026-03-03 | 2026-04-07 | Completed
M6155 | P1212 | Design Approval | 2026-05-30 | 2026-06-19 | Completed
M6156 | P1213 | Foundation | 2024-04-10 | 2024-04-15 | Completed
M6157 | P1213 | Land Acquisition | 2024-07-01 | 2024-07-01 | Delayed
M6158 | P1213 | Safety Inspection | 2024-09-21 | 2024-10-26 | Completed
M6159 | P1213 | Structural Work | 2024-12-12 | 2024-12-12 | Completed
M6160 | P1213 | Major Construction | 2025-03-04 | 2025-03-04 | Completed
M6161 | P1213 | Design Approval | 2025-05-25 | null | Delayed
M6162 | P1214 | Safety Inspection | 2024-04-12 |  | In Progress
M6163 | P1214 | Foundation | 2024-08-10 | 2024-10-09 | Completed
M6164 | P1214 | Design Approval | 2024-12-08 | 2025-02-06 | Delayed
M6165 | P1214 | Testing | 2025-04-07 | 2025-06-06 | Completed
M6166 | P1215 | Major Construction | 2023-08-22 | 2023-09-11 | Completed
M6167 | P1215 | Structural Work | 2023-12-10 | 2023-12-10 | Completed
M6168 | P1215 | Safety Inspection | 2024-03-30 | 2024-04-09 | Delayed
M6169 | P1215 | Foundation | 2024-07-18 | 2024-07-28 | Completed
M6170 | P1216 | Design Approval | 2025-05-03 | 2025-05-23 | Completed
M6171 | P1216 | Safety Inspection | 2025-08-30 |  | Not Started
M6172 | P1216 | Structural Work | 2025-12-27 | 2026-01-31 | Completed
M6173 | P1216 | Foundation | 2026-04-25 |  | Not Started
M6174 | P1216 | Final Handover | 2026-08-21 |  | Not Started
M6175 | P1216 | Testing | 2026-12-18 | 2026-12-28 | Delayed
M6176 | P1216 | Major Construction | 2027-04-16 | 2027-06-15 | Delayed
M6177 | P1217 | Foundation | 2022-12-08 | 2022-12-28 | Completed
M6178 | P1217 | Design Approval | 2023-02-09 | 2023-03-01 | Delayed
M6179 | P1217 | Testing | 2023-04-13 | 2023-05-03 | Delayed
M6180 | P1217 | Final Handover | 2023-06-14 | 2023-06-24 | Completed
M6181 | P1217 | Safety Inspection | 2023-08-16 | 2023-09-05 | Completed
M6182 | P1217 | Major Construction | 2023-10-18 | 2023-11-04 | Delayed
M6183 | P1218 | Final Handover | 2022-06-06 | 2022-06-16 | Completed
M6184 | P1218 | Design Approval | 2022-09-07 | 2022-10-12 | Delayed
M6185 | P1218 | Safety Inspection | 2022-12-09 | 2022-12-19 | Completed
M6186 | P1218 | Structural Work | 2023-03-12 | 2023-05-11 | Completed
M6187 | P1219 | Foundation | 2023-01-04 | 2023-01-04 | Delayed
M6188 | P1219 | Land Acquisition | 2023-05-22 | 2023-05-22 | Delayed
M6189 | P1219 | Testing | 2023-10-07 | 2023-10-09 | Delayed
M6190 | P1219 | Major Construction | 2024-02-21 | 2024-03-02 | Delayed
M6191 | P1219 | Final Handover | 2024-07-08 | 2024-09-06 | Completed
M6192 | P1220 | Major Construction | 2025-10-31 | 2025-12-05 | Completed
M6193 | P1220 | Land Acquisition | 2026-01-01 | 2026-01-03 | Delayed
M6194 | P1220 | Design Approval | 2026-03-03 | 2026-04-07 | Completed
M6195 | P1220 | Testing | 2026-05-04 | 2026-06-08 | Completed
M6196 | P1220 | Safety Inspection | 2026-07-05 | 2026-09-03 | Delayed
M6197 | P1220 | Structural Work | 2026-09-04 | 2026-09-14 | Completed
M6198 | P1220 | Foundation | 2026-11-05 | 2026-11-07 | Delayed
M6199 | P1221 | Final Handover | 2025-08-15 |  | In Progress
M6200 | P1221 | Land Acquisition | 2025-12-11 | 2025-12-11 | Completed
M6201 | P1221 | Structural Work | 2026-04-08 |  | Not Started
M6202 | P1221 | Major Construction | 2026-08-04 | 2026-08-14 | Delayed
M6203 | P1221 | Design Approval | 2026-11-30 |  | Not Started
M6204 | P1221 | Safety Inspection | 2027-03-28 |  | In Progress
M6205 | P1221 | Testing | 2027-07-24 | 2027-08-03 | Delayed
M6206 | P1222 | Structural Work | 2023-02-20 |  | In Progress
M6207 | P1222 | Testing | 2023-05-02 |  | In Progress
M6208 | P1222 | Land Acquisition | 2023-07-13 |  | Pending
M6209 | P1222 | Major Construction | 2023-09-22 | 2023-10-27 | Completed
M6210 | P1222 | Safety Inspection | 2023-12-02 | 2023-12-12 | Completed
M6211 | P1222 | Design Approval | 2024-02-12 | 2024-03-18 | Completed
M6212 | P1222 | Foundation | 2024-04-23 | 2024-05-03 | Completed
M6213 | P1223 | Testing | 2023-12-20 |  | Delayed
M6214 | P1223 | Major Construction | 2024-05-20 | 2024-07-19 | N/A
M6215 | P1223 | Final Handover | 2024-10-19 | 2024-12-18 | Completed
M6216 | P1223 | Structural Work | 2025-03-20 | 2025-03-25 | Completed
M6217 | P1223 | Design Approval | 2025-08-19 | 2025-08-21 | Completed
M6218 | P1224 | Foundation | 2025-10-12 |  | In Progress
M6219 | P1224 | Major Construction | 2026-01-06 | 2026-01-08 | Completed
M6220 | P1224 | Structural Work | 2026-04-02 |  | In Progress
M6221 | P1224 | Land Acquisition | 2026-06-27 |  | In Progress
M6222 | P1224 | Testing | 2026-09-21 |  | Pending
M6223 | P1225 | Design Approval | 2024-04-17 | 2024-04-17 | Completed
M6224 | P1225 | Foundation | 2024-10-01 | 2024-10-06 | Completed
M6225 | P1225 | Structural Work | 2025-03-17 | 2025-05-16 | Completed
M6226 | P1225 | Land Acquisition | 2025-08-31 | 2025-10-30 | Completed
M6227 | P1226 | Final Handover | 2023-08-06 | 2023-10-05 | Completed
M6228 | P1226 | Safety Inspection | 2024-01-02 | 2024-01-02 | Completed
M6229 | P1226 | Structural Work | 2024-05-30 | 2024-05-30 | Completed
M6230 | P1226 | Land Acquisition | 2024-10-26 | 2024-10-28 | Completed
M6231 | P1227 | Final Handover | 2025-10-02 | 2025-10-04 | Delayed
M6232 | P1227 | Testing | 2025-12-30 | 2026-02-28 | Completed
M6233 | P1227 | Land Acquisition | 2026-03-29 | 2026-05-28 | Delayed
M6234 | P1227 | Design Approval | 2026-06-26 | 2026-07-16 | Completed
M6235 | P1227 | Foundation | 2026-09-22 | 2026-09-27 | Delayed
M6236 | P1227 | Major Construction | 2026-12-20 | 2027-01-24 | Completed
M6237 | P1227 | Safety Inspection | 2027-03-19 | 2027-05-18 | Delayed
M6238 | P1228 | Foundation | 2023-02-16 | 2023-04-17 | Completed
M6239 | P1228 | Safety Inspection | 2023-05-14 | 2023-05-24 | Completed
M6240 | P1228 | Structural Work | 2023-08-09 | 2023-09-13 | Completed
M6241 | P1228 | Testing | 2023-11-03 | 2023-11-08 | Delayed
M6242 | p1228 | Major Construction | 2024-01-29 | 2024-01-31 | Delayed
M6243 | P1229 | Safety Inspection | 2023-09-07 |  | Pending
M6244 | P1229 | Final Handover | 2024-01-21 |  | Not Started
M6245 | P1229 | Land Acquisition | 2024-06-05 | 2024-07-27 | Delayed
M6246 | P1229 | Design Approval | 2024-10-19 | 2024-11-23 | Completed
M6247 | P1230 | Testing | 2024-01-25 | 2024-02-29 | Completed
M6248 | P1230 | Land Acquisition | 2024-03-17 |  | Not Started
M6249 | P1230 | Foundation | 2024-05-08 |  | Not Started
M6250 | P1230 | Major Construction | 2024-06-29 | 2024-07-04 | Delayed
M6251 | P1230 | Design Approval | 2024-08-20 |  | In Progress
M6252 | P1230 | Final Handover | 2024-10-11 | 2024-10-31 | Completed
M6253 | P1231 | Foundation | 2022-12-25 | 2023-02-23 | Completed
M6254 | P1231 | Major Construction | 2023-03-14 | 2023-05-13 | Completed
M6255 | P1231 | Safety Inspection | 2023-06-01 | 2023-07-31 | Completed
M6256 | P1231 | Final Handover | 2023-08-19 | 2023-11-06 | Delayed
M6257 | P1231 | Design Approval | 2023-11-06 | 2023-11-06 | Completed
M6258 | P1231 | Land Acquisition | 2024-01-24 | 2024-02-13 | Completed
M6259 | P1231 | Structural Work | 2024-04-12 | 2024-06-11 | Completed
M6260 | P1232 | Major Construction | 2023-07-01 |  | Not Started
M6261 | P1232 | Final Handover | 2023-10-19 | 2023-12-02 | Delayed
M6262 | P1232 | Testing | 2024-02-07 | 2024-02-12 | Completed
M6263 | P1232 | Land Acquisition | 2024-05-27 | 2024-07-12 | Delayed
M6264 | P1232 | Structural Work | 2024-09-14 | 2024-10-04 | Completed
M6265 | P1232 | Design Approval | 2025-01-03 |  | In Progress
M6266 | P1232 | Safety Inspection | 2025-04-23 | 2025-04-25 | Delayed
M6267 | P1233 | Design Approval | 2023-11-23 | 2023-11-28 | Delayed
M6268 | P1233 | Land Acquisition | 2024-01-10 | 2024-01-30 | Delayed
M6269 | P1233 | Safety Inspection | 2024-02-27 | 2024-03-18 | Delayed
M6270 |  | Structural Work | 2024-04-15 |  | Delayed
M6271 | P1233 | Final Handover | 2024-06-02 | 2024-06-12 | Completed
M6272 | P1233 | Major Construction | 2024-07-20 | 2024-07-22 | Delayed
M6273 | P1233 | Testing | 2024-09-06 | 2024-09-08 | Completed
M6274 | P1234 | Final Handover | 2023-07-03 |  | Pending
M6275 | P1234 | N/A | 2023-11-08 |  | In Progress
M6276 | P1234 | Land Acquisition | 2024-03-16 | 2024-03-21 | Completed
M6277 | P1234 | Design Approval | 2024-07-22 | 2024-07-24 | Completed
M6278 | P1234 | Foundation | 2024-11-27 | 2024-12-02 | Completed
M6279 | P1235 | Final Handover | 2025-02-24 |  | In Progress
M6280 | P1235 | Land Acquisition | 2025-07-02 |  | Pending
M6281 | P1235 | Design Approval | 2025-11-06 | 2025-12-11 | Delayed
M6282 | P1235 | Testing | 2026-03-14 | 2026-04-03 | Completed
M6283 | P1235 | Structural Work | 2026-07-19 | 2026-07-19 | Delayed
M6284 | P1235 | Safety Inspection | 2026-11-24 | 2026-11-29 | Delayed
M6285 | P1236 | Safety Inspection | 2022-06-04 | 2022-06-14 | Delayed
M6286 | P1236 | Structural Work | 2022-10-02 | 2022-10-04 | Completed
M6287 | P1236 | Testing | 2023-01-30 | 2023-02-19 | Delayed
M6288 | P1236 | Major Construction | 2023-05-30 | 2023-06-09 | Completed
M6289 | P1236 | Design Approval | 2023-09-27 | N/A | Delayed
M6290 | P1236 | Land Acquisition | 2024-01-25 | 2024-02-29 | Completed
M6291 | P1237 | Land Acquisition | 2024-05-27 |  | Pending
M6292 | P1237 | Major Construction | 2024-07-20 | 2024-08-09 | Completed
M6293 | P1237 | Testing | 2024-09-12 |  | Not Started
M6294 | P1237 | Foundation | 2024-11-05 | 2024-11-15 | Completed
M6295 | P1237 | Final Handover | 2024-12-29 | 2025-01-18 | Completed
M6296 | P1238 | Major Construction | 2026-01-20 |  | Not Started
M6297 | P1238 | Safety Inspection | 2026-07-20 | 2026-09-18
M6298 | P1238 | Design Approval | 2027-01-17 | 2027-01-17 | Delayed
M6299 | P1238 | Testing | 2027-07-17 |  | Pending
M6300 | P1239 | Safety Inspection | 2025-10-08 | 2025-10-08 | Completed
M6301 | P1239 | Design Approval | 2026-02-08 | 2026-02-13 | Completed
M6302 | P1239 | Structural Work | 2026-06-11 | 2026-08-10 | Completed
M6303 | P1239 | Land Acquisition | 2026-10-13 | 2026-10-23 | Completed
M6304 | P1239 | Foundation | 2027-02-13 | 2027-02-18 | Completed
M6305 | P1239 | Final Handover | 2027-06-16 | 2027-06-16 | Completed
M6306 | P1240 | Design Approval | 2022-11-20 |  | Pending
M6307 | P1240 | Foundation | 2023-01-23 | 2023-01-25 | Completed
M6308 | P1240 | Final Handover | 2023-03-29 | 2023-05-28 | Delayed
M6309 | P1240 | Structural Work | 2023-06-01 |  | In Progress
M6310 | P1240 | Safety Inspection | 2023-08-04 | 2023-08-14 | Delayed
M6311 | P1240 | Testing | 2023-10-08 | 2023-10-08 | Delayed
M6312 | P1240 | Major Construction | 2023-12-11 | 2023-12-28 | Delayed
M6313 | P1241 | Design Approval | 2025-02-06 | 2025-02-06 | Completed
M6314 | P1241 | Final Handover | 2025-05-04 | 2025-05-06 | Completed
M6315 | P1241 | Major Construction | 2025-07-30 | 2025-08-01 | Completed
M6316 | P1241 | Safety Inspection | 2025-10-25 | 2025-11-04 | Delayed
M6317 | P1241 | Foundation | 2026-01-20 | 2026-03-21 | Delayed
M6318 | P1241 | Structural Work | 2026-04-17 | 2026-05-07 | Completed
M6319 | P1242 | Land Acquisition | N/A |  | In Progress
M6320 | P1242 | Final Handover | 2022-04-11 |  | Not Started
M6321 | P1242 | Structural Work | 2022-05-28 | 2022-07-27 | Completed
M6322 | P1242 | Foundation | 2022-07-15 | 2022-08-19 | Completed
M6323 | P1242 | Major Construction | 2022-08-31 | 2022-09-10 | Completed
M6324 | P1243 | Major Construction | 2025-12-24 | 2025-12-29 | Completed
M6325 | P1243 | Structural Work | 2026-04-15 | 2026-05-20 | Delayed
M6326 | P1243 | Design Approval | 2026-08-04 | 2026-09-08 | Completed
M6327 | P1243 | Final Handover | 2026-11-24 | 2026-12-04 | Completed
M6328 | P1243 | Foundation | N/A | 2027-04-19 | Completed
M6329 | p1244 | Final Handover | 2025-01-18 | 2025-02-22 | Delayed
M6330 | P1244 | Land Acquisition | 2025-03-16 |  | Not Started
M6331 | P1244 | Safety Inspection | 2025-05-13 | 2025-06-17 | Completed
M6332 | P1244 | Design Approval | 2025-07-09 | 2025-09-07 | Delayed
M6333 | P1245 | Testing | 2024-01-31 | 2024-02-02 | Completed
M6334 | P1245 | Safety Inspection | 2024-07-12 | 2024-07-17 | Completed
M6335 | P1245 | Structural Work | 2024-12-23 | 2024-12-25 | Completed
M6336 | P1245 | Major Construction | 2025-06-04 | 2025-08-03 | Delayed
M6337 | P1246 | Design Approval | 2024-06-02 | 2024-06-12 | Completed
M6338 | P1246 | Safety Inspection | 2024-07-16 | 2024-07-26 | Completed
M6339 | P1246 | Major Construction | 2024-08-29 | 2024-10-28 | Delayed
M6340 | P1246 | Foundation | 2024-10-12 | 2024-10-17 | Delayed
M6341 | P1246 | Final Handover | 2024-11-25 | 2024-11-27 | Completed
M6342 | P1247 | Foundation | 2023-11-30 | 2023-12-20 | Completed
M6343 | P1247 | Testing | 2024-02-07 | 2024-03-13 | Completed
M6344 | P1247 | Land Acquisition | 2024-04-16 | 2024-05-21 | Completed
M6345 | P1247 | Design Approval | 2024-06-24 | 2024-07-29 | Completed
M6346 | P1248 | Land Acquisition | 2024-07-11 | 2024-08-15 | Delayed
M6347 | P1248 | Structural Work | 2024-09-27 | 2024-10-17 | Completed
M6348 | P1248 | Testing | 2024-12-13 |  | Pending
M6349 | P1248 | Final Handover | 2025-03-01 | 2025-03-11 | Delayed
M6350 | P1248 | Foundation | 2025-05-18 | 2025-05-28 | Completed
M6351 | P1248 | Design Approval |  | 2025-08-23 | Completed
M6352 | P1248 | Safety Inspection | 2025-10-20 |  | Pending
M6353 | P1249 | Design Approval | 2023-07-06 | 2023-07-06 | Completed
M6354 | P1249 | Final Handover | 2023-09-11 | 2023-11-10 | Completed
M6355 | p1249 | Safety Inspection | 2023-11-17 | 2023-12-22 | Completed
M6356 | P1249 | Testing | N/A | 2024-01-26 | Completed
M6357 | P1249 | Foundation | 2024-03-31 | 2024-04-05 | Completed
M6358 | P1249 | Major Construction | 2024-06-06 | 2024-06-26 | Completed
M6359 | P1249 | Land Acquisition | 2024-08-12 | 2024-10-11 | Delayed
M6360 | P1250 | Final Handover | 2023-03-22 | 2023-03-22 | Delayed
M6361 | P1250 | Major Construction | 2023-09-06 | 2023-11-05 | Completed
M6362 | P1250 | Land Acquisition | 2024-02-20 | 2024-02-20 | Delayed
M6363 | P1250 | Testing | 2024-08-06 | 2024-08-26 | Delayed
M6364 | P1211 | Structural Work | 2025-07-26 | 2025-07-26 | Completed
M6365 | P1199 | Land Acquisition | 2025-11-23 |  | In Progress
M6366 | P1186 | Structural Work | 2023-06-01 | 2023-07-06 | Completed
M6367 | P1140 | Major Construction | 2022-06-24 | 2022-07-04 | Completed
M6368 | P1117 | Structural Work | 2025-08-16 |  | Pending
M6369 | P1051 | Land Acquisition | 2024-11-07 | 2024-11-09 | Completed
M6370 | P1136 | Design Approval | 2025-06-29 |  | In Progress
M6371 | P1109 | Testing | 2026-07-15 | 2026-07-20 | Completed
M6372 | P1076 | Major Construction | 2025-10-14 | 2025-10-14 | Completed
M6373 | P1106 | Structural Work | 2022-07-04 |  | Delayed
M6374 | P1138 | Major Construction | 2023-03-08 | 2023-04-12 | Completed
M6375 |  | Major Construction | 2024-07-01 | 2024-08-05 | Completed
M6376 | P1004 | Land Acquisition | 2026-01-22 | 2026-03-23 | Completed